## Programs
|  | Annex A: Infrastructure projects 2021–2031+ | [21 empty] | Estimated Allocation (DATA ENTRY)
|  |  |  | Prioritisation |  |  |  | Total No. Projects | Total projects budget | Total | Current | Yr 1 | Yr 2 | Yr 3 | Yr 4 | Yr 5 | Yr 6 | Yr 7 | Yr 8 | Yr 9 | Yr 10 | Yr 11+ |  | Committed | Yr 1 | Yr 2 | Yr 3 | Yr 4 | Yr 5 | Yr 6 | Yr 7 | Yr 8 | Yr 9 | Yr 10 | Yr 11+
Row | Program Name (alphabetical) | Sector | Program Budget | Benefit | Scale | Sort | Rating |  |  | 10-yr Alloc. ($million) | 20/21 | 21/22 | 22/23 | 23/24 | 24/25 | 25/26 | 26/27 | 27/28 | 28/29 | 29/30 | 30/31 | 31+ |  | 20/21 | 21/22 | 22/23 | 23/24 | 24/25 | 25/26 | 26/27 | 27/28 | 28/29 | 29/30 | 30/31 | 31+
22 | Rarotonga Education Infrastructure Program | Education | 25 | 4 | 4.2 | 2.56 | MP | 2 | 25 | 25 | 0 | 0 | 0 | 6.25 | 0 | 1.25 | 7.5 | 5 | 5 | 0 | 0 | 0 | 100% |  |  |  | 25% |  | 5% | 30% | 20% | 20%
28 | Rarotonga Sanitation Improvements | Sanitation | 55 | 4.7 | 4.25 | 2.46 | MP | 3 | 55.16 | 55 | 0 | 0 | 2.75 | 2.75 | 0 | 2.75 | 2.75 | 11 | 13.75 | 13.75 | 5.5 | 0 | 100% |  |  | 5% | 5% |  | 5% | 5% | 20% | 25% | 25% | 10%
3 | Aitutaki Renewable Energy Program | Energy | 7 | 4.05 | 3.75 | 2.19 | MP | 1 | 7 | 7 | 0 | 0 | 0 | 3.5 | 3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% |  |  |  | 50% | 50%
6 | National Health Infrastructure Program | Health | 76.2 | 4.65 | 3.9 | 2.19 | MP | 4 | 76.15 | 76.0969 | 0 | 1.1508 | 6.096 | 11.43 | 15.5102 | 15.24 | 11.43 | 11.43 | 3.81 | 0 | 0 | 0 | 99.86% |  | 1.51% | 8% | 15% | 20.35% | 20% | 15% | 15% | 5%
18 | Rarotonga Airport Upgrades | Air | 67.1 | 4.3 | 3.75 | 2.14 | MP | 10 | 67.06 | 46.97 | 3.355 | 6.71 | 3.355 | 6.71 | 0 | 0 | 0 | 0 | 10.065 | 10.065 | 10.065 | 16.775 | 100% | 5% | 10% | 5% | 10% |  |  |  |  | 15% | 15% | 15% | 25%
24 | Rarotonga Government Buildings | Buildings | 66 | 4.35 | 3.7 | 2.09 | MP | 2 | 66 | 49.5 | 0 | 3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 9.9 | 23.1 | 13.2 | 16.5 | 100% |  | 5% | [6 empty] | 15% | 35% | 20% | 25%
23 | Rarotonga Energy Upgrades | Energy | 36.1 | 4.7 | 3.7 | 2.02 | MP | 7 | 36.067 | 32.49 | 3.61 | 3.61 | 3.61 | 3.61 | 3.61 | 3.61 | 3.61 | 3.61 | 3.61 | 3.61 | 0 | 0 | 100% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10%
29 | Rarotonga Solid Waste Management Program | Waste | 6.4 | 5 | 3.75 | 2 | MP | 5 | 6.36 | 6.4 | 0 | 0.96 | 0 | 4.8 | 0.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% |  | 15% |  | 75% | 10%
7 | National Tertiary Campus Improvements | Education | 12.7 | 4.05 | 3.45 | 1.95 | MP | 2 | 12.7 | 12.7 | 0 | 0.5 | 0.2 | 3 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 100% |  | 3.937% | 1.575% | 23.62% | 47.24% | 23.62%
9 | Northern Airport Improvements | Air | 19.7 | 4 | 3.2 | 1.76 | MP | 3 | 19.66 | 19.5397 | 0.16033 | 3.5071 | 9.5193 | 0 | 6.5132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0.8138% | 17.8% | 48.32% |  | 33.06%
32 | Southern Airport Improvements | Air | 13.4 | 4 | 3.2 | 1.76 | MP | 5 | 13.35 | 13.4 | 0 | 0.67 | 3.35 | 3.35 | 2.01 | 4.02 | 0 | 0 | 0 | 0 | 0 | 0 | 100% |  | 5% | 25% | 25% | 15% | 30%
30 | Rarotonga Township Enhancements | Municipal | 16.3 | 4.65 | 3.15 | 1.59 | MP | 6 | 16.25 | 16.3752 | 0 | 0.815 | 0.815 | 0.815 | 1.7052 | 3.26 | 3.26 | 4.89 | 0.815 | 0 | 0 | 0 | 100.5% |  | 5% | 5% | 5% | 10.46% | 20% | 20% | 30% | 5%
25 | Rarotonga Harbour Improvements | Marine | 6.3 | 4.05 | 2.95 | 1.55 | MP | 4 | 6.3 | 6.3 | 0 | 0.3 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 100% |  | 4.762% |  |  |  |  | 47.62% | 47.62%
31 | Rarotonga Water Security Program | Water | 46.2 | 4.7 | 3.05 | 1.5 | MP | 10 | 46.1706 | 45.1097 | 2.1013 | 9.5871 | 7.5048 | 6.0038 | 6.0038 | 5.0032 | 5.0032 | 3.0019 | 3.0019 | 0 | 0 | 0 | 102.2% | 4.548% | 20.75% | 16.24% | 13% | 13% | 10.83% | 10.83% | 6.498% | 6.498%
16 | Pa Enua Cyclone Shelter Program | Buildings | 4.9 | 2.35 | 3.9 | 2.65 | CP | 4 | 4.85 | 4.9 | 0 | 0.735 | 1.96 | 1.96 | 0.245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% |  | 15% | 40% | 40% | 5%
27 | Rarotonga Road Reconstruction Program | Road | 18.8 | 2.95 | 3.5 | 2.21 | CP | 1 | 18.8 | 18.8 | 0 | 4.7 | 4.7 | 4.7 | 4.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% |  | 25% | 25% | 25% | 25%
17 | Pukapuka Harbour Improvements | Marine | 4.4 | 2 | 3.25 | 2.2 | CP | 2 | 4.36 | 4.4 | 0 | 0 | 0 | 4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% |  |  |  | 100%
11 | Northern Harbour Improvements | Marine | 26.4 | 3.65 | 3.6 | 2.15 | CP | 6 | 26.38 | 26.4 | 0 | 0 | 5.28 | 1.32 | 9.24 | 10.56 | 0 | 0 | 0 | 0 | 0 | 0 | 100% |  |  | 20% | 5% | 35% | 40%
5 | National Coastal Protection Program | Coastal | 31 | 3.7 | 3.6 | 2.14 | CP | 7 | 31.2 | 31 | 0 | 1.55 | 1.55 | 3.1 | 3.1 | 4.65 | 3.1 | 3.1 | 3.1 | 3.1 | 4.65 | 0 | 100% |  | 5% | 5% | 10% | 10% | 15% | 10% | 10% | 10% | 10% | 15%
38 | Southern Water Security Program | Water | 7.9 | 2.4 | 3.05 | 1.96 | CP | 7 | 7.865 | 7.505 | 0.395 | 0.79 | 3.16 | 1.975 | 0.79 | 0.79 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 5% | 10% | 40% | 25% | 10% | 10%
20 | Rarotonga Buildings Program | Buildings | 11 | 2.65 | 3.1 | 1.95 | CP | 3 | 11 | 9.9 | 0 | 0.55 | 2.2 | 1.65 | 1.1 | 0 | 0 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 100% |  | 5% | 20% | 15% | 10% |  |  | 10% | 10% | 10% | 10% | 10%
14 | Northern Solid Waste Program | Waste | 0.1 | 2.75 | 3.1 | 1.93 | CP | 1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
21 | Rarotonga Cyclone Shelter Program | Buildings | 30.3 | 2.65 | 3.05 | 1.91 | CP | 2 | 30.3 | 15.15 | 0 | 0 | 0 | 3.03 | 3.03 | 3.03 | 3.03 | 3.03 | 0 | 0 | 0 | 15.15 | 100% |  |  |  | 10% | 10% | 10% | 10% | 10% |  |  |  | 50%
15 | Northern Water Security Program | Water | 1.3 | 2.7 | 3.05 | 1.9 | CP | 2 | 1.32 | 0.91 | 0.39 | 0.39 | 0.39 | 0.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 30% | 30% | 30% | 10%
2 | Aitutaki Harbour and Marina Improvements | Marine | 14.8 | 3.65 | 3.25 | 1.87 | CP | 2 | 14.8 | 8.88 | 1.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.96 | 2.96 | 2.96 | 4.44 | 100% | 10% | [7 empty] | 20% | 20% | 20% | 30%
37 | Southern Solid Waste Management Program | Waste | 0.2 | 3.35 | 3.15 | 1.85 | CP | 1 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
1 | Aitutaki Airport Improvements | Air | 3.2 | 3.05 | 3 | 1.79 | CP | 2 | 3.19 | 3.2 | 0 | 0 | 0 | 0.48 | 2.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% |  |  |  | 15% | 85%
19 | Rarotonga Bridge Renewals | Road | 18.5 | 2.6 | 2.85 | 1.76 | CP | 4 | 18.5 | 18.5 | 0 | 1.85 | 3.7 | 3.7 | 1.85 | 1.85 | 1.85 | 1.85 | 1.85 | 0 | 0 | 0 | 100% |  | 10% | 20% | 20% | 10% | 10% | 10% | 10% | 10%
33 | Southern Harbour Improvements | Marine | 3.3 | 3.05 | 2.95 | 1.75 | CP | 4 | 3.345 | 3.3 | 0 | 0.825 | 0 | 1.155 | 0 | 0 | 0 | 0.33 | 0.33 | 0.33 | 0.33 | 0 | 100% |  | 25% |  | 35% |  |  |  | 10% | 10% | 10% | 10%
8 | National Vessel Program | Marine | 10 | 3 | 2.9 | 1.72 | CP | 1 | 10 | 10 | 0 | 0 | 0 | 0 | 2 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 100% |  |  |  |  | 20% | 80%
4 | Aitutaki Water Security Program | Water | 10.7 | 3.7 | 3.05 | 1.7 | CP | 3 | 10.7 | 10.165 | 0.5 | 0 | 0.535 | 4.815 | 4.815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99.67% | 4.673% |  | 5% | 45% | 45%
35 | Southern Road Improvement Program | Road | 5 | 3 | 2.85 | 1.68 | CP | 3 | 5 | 5 | 0 | 1.6 | 3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% |  | 32% | 68%
12 | Northern Renewable Energy Program | Energy | 5 | 3.75 | 2.95 | 1.61 | CP | 1 | 5 | 5 | 0 | 0 | 2.1 | 2.1 | 0.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% |  |  | 42% | 42% | 16%
36 | Southern Sanitation Improvements | Sanitation | 5.3 | 2.7 | 2.75 | 1.66 |  | 2 | 5.15 | 5.3 | 0 | 0.265 | 0.265 | 0.53 | 2.12 | 0 | 1.06 | 1.06 | 0 | 0 | 0 | 0 | 100% |  | 5% | 5% | 10% | 40% |  | 20% | 20%
13 | Northern Sanitation Improvements | Sanitation | 3.2 | 2.7 | 2.5 | 1.46 |  | 2 | 3.17 | 3.2 | 0 | 0.97918 | 0.20189 | 0 | 0 | 0 | 1.0095 | 1.0095 | 0 | 0 | 0 | 0 | 100% |  | 30.6% | 6.309% |  |  |  | 31.55% | 31.55%
10 | Northern Building Improvements | Buildings | 1.5 | 2.35 | 2.4 | 1.45 |  | 5 | 1.5 | 1.5 | 0 | 0.3 | 0.6 | 0.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% |  | 20% | 40% | 40%
26 | Rarotonga Road Improvements | Road | 5.4 | 3 | 2.4 | 1.32 |  | 5 | 5.412 | 5.4 | 0 | 1.89 | 0.54 | 2.16 | 0.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% |  | 35% | 10% | 40% | 15%
34 | Southern ICT Connectivity | ICT | 11.7 | 4.05 | 2.6 | 1.27 |  | 1 | 10 | 7.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.34 | 2.34 | 2.34 | 4.68 | 100% | [8 empty] | 20% | 20% | 20% | 40%
|  |  | 687.3 |  |  |  |  | 135 | 685.3696 | 617.3115 | 11.9917 | 47.5342 | 67.782 | 90.0238 | 82.8125 | 67.0132 | 46.6026 | 53.4114 | 61.6319 | 60.355 | 40.145 | 58.645
Note on M50: Glenn: These numbers may come from MFEM as should already be committed but make assumption for now

## Projects
| Cook Islands National Infrastructure Investment Plan (2021 Release) | [9 empty] | Category |  |  |  | 10-yr Budget
[11 empty] | Criticality | Complexity | Climate | Stimulus | Feasibility | Design | Construct | Estimated Start/Duration
Row | Sector Code | Lead Agency | Program | Project Name | Brief Description | Project Type | Status | Island Serviced | Best Estimate | Funding Source | [7 empty] | 20/21 | 21/22 | 22/23 | 23/24 | 24/25 | 25/26 | 26/27 | 27/28 | 28/29 | 29/30 | 30/31 | Notes
1 | Air | AACI | Rarotonga Airport Upgrades | Airport Arrival Terminal - Phase 2 | Replicate phase 1 building to increase size | Upgrade |  | Rarotonga | 10900 | [6 empty] | X | X | [8 empty] | X | X |  | Less aircraft movements could see pro 'sit'
2 | Air | AACI | Rarotonga Airport Upgrades | Airport Baggage Makeup Area | Redesign rebuild of original area should sit with above. | Upgrade |  | Rarotonga | 5600 | [6 empty] | X | X |  |  | X | X | [7 empty] | Await review of Master Plan
3 | Air | AACI | Rarotonga Airport Upgrades | Airport Check-in Upgrade | Redesign rebuild of original area | Upgrade |  | Rarotonga | 3700 | [6 empty] | X | X |  |  | X | X | [7 empty] | Await review of Master Plan
4 | Air | AACI | Rarotonga Airport Upgrades | Airport Cyclone Protection Works | Western end airfield protection | New |  | Rarotonga | 1600 |  | P2 |  | X |  |  | X | X | [11 empty] | Some funding ex Climate Adaption
5 | Air | AACI | Rarotonga Airport Upgrades | Airport Departure Terminal Upgrade | Increase Size | Upgrade |  | Rarotonga | 11100 | [6 empty] | X | X | [9 empty] | X | X | Ditto -- Await review Master Plan
6 | Air | AACI | Rarotonga Airport Upgrades | Airport Master Plan | Business plan and strategy | Study | ON | Rarotonga | 760 | ADB |  |  |  |  | X |  |  | X | [10 empty] | Aust Con appointed : Review due to Covid
7 | Air | AACI | Rarotonga Airport Upgrades | Airport Relocation of Control Tower | Move Tower to southern side of airport | New |  | Rarotonga | 12900 | [6 empty] | X | X | [10 empty] | X | A very long term project
8 | Air | AACI | Aitutaki Airport Improvements | Aitutaki Passenger Terminal Improvements | Extension and full rebuild | Upgrade |  | Aitutaki | 1190 | [6 empty] | X | X |  |  |  | X | X | [6 empty] | Desirable but maybe not necessary
9 | Air | ICI | Aitutaki Airport Improvements | Aitutaki Runway Reclamation | Northern end protection of safety runoff area. | Renew |  | Aitutaki | 2000 | [6 empty] | X | X | [5 empty] | X | [5 empty] | Avaition Requirement
10 | Air | ICI | Southern Airport Improvements | Atiu Upgrade to Regional Turbo Prop Runway | Feasibility study and construction for CAA Part 139 | Upgrade |  | Atiu | 5460 | [6 empty] | X | X |  | X | X | X | [7 empty] | Was high priority in 2015 NIIP !!
11 | Air | AACI | Rarotonga Airport Upgrades | Code C Apron Expansion | Extension of Apron to accommodate extra aircraft | Upgrade |  | Rarotonga | 8500 | [6 empty] | X | X | [10 empty] | X | Ditto -- Await review Master Plan
12 | Air | AACI | Rarotonga Airport Upgrades | Eastern End Safety Area | Extend runway to provide 200m runoff zone | Upgrade |  | Rarotonga | 6000 |  | P1 |  |  |  |  | X | X |  | X | X | [8 empty] | Land Purchase underway: Aviation requirement
13 | Air | ICI | Southern Airport Improvements | Mangaia Airport Runway Upgrade | Relocate & upgrade runway (feasibility and build) | Upgrade |  | Mangaia | 5260 | [6 empty] | X | X |  |  |  | X | X | X | [5 empty] | Low Priority
14 | Air | ICI | Northern Airport Improvements | Manihiki Upgrade to Regional Turbo Prop Runway | Feasibility study and construction for CAA Part 139 | New |  | Manihiki | 6660 | CIG |  |  |  |  | X | X | X | X | X | X | [8 empty] | Req for design tenders underway Mar 21.
15 | Air | ICI | Southern Airport Improvements | Mauke Airport Fencing Improvements | Fencing to control roaming animals | Upgrade |  | Mauke | 150 |  | P1 | [5 empty] | X |  | X | [9 empty] | A safety isue that should proceed.
16 | Air | ICI | Southern Airport Improvements | Mauke Airport Improvements | Detailed design | Upgrade |  | Mauke | 1360 | [6 empty] | X | X |  | X |  | X | [7 empty] | Sits with Sth Group feasibility study on airports
17 | Air | ICI | Southern Airport Improvements | Mitiaro Airport Runway Upgrade | Detailed design | Upgrade |  | Mitiaro | 1120 | [6 empty] | X | X |  |  | X | [8 empty] | Sits with Sth Group feasibility study on airports
18 | Air | ICI | Northern Airport Improvements | Penrhyn Airport Runway Upgrade | Detailed design | Upgrade |  | Penrhyn | 6500 | [6 empty] | X | X |  |  | X | [8 empty] | Sits with Manihiki ( Pos Aussie Funding )
19 | Air | ICI | Northern Airport Improvements | Pukapuka Airport Runway Upgrade | Detailed design | Upgrade |  | Pukapuka | 6500 | [6 empty] | X | X |  |  |  |  | X | [6 empty] | Consideration at time of Manihiki & Penrhyn ??
20 | Air | AACI | Rarotonga Airport Upgrades | Runway Repairs | Runway slab repairs | Renew | ON | Rarotonga | 6000 | NZ Aid | P1 |  |  |  |  | X | X | X | X | [9 empty] | Replacement Slab Contract has been let.
21 | Buildings | ICI | Rarotonga Cyclone Shelter Program | Cyclone Shelters Structural Review | Pa Enua and Rarotonga - Research and Investigations | Study |  | Cook Islands | 300 | CIG | P1 | Cat.5 | X |  | X |  |  |  | X | X | [8 empty] | To be scoped and designed
22 | Buildings | CIIC | Pa Enua Cyclone Shelter Program | Manihiki Major Renovations to Cyclone Centres |  | Upgrade |  | Manihiki | 300 | CIG | P2 |  | X |  |  |  | X |  | X
23 | Buildings | CIIC | Northern Building Improvements | Manihiki New Government Building (Replace MoJ) |  | New |  | Manihiki | 300 | CIG | [6 empty] | X |  |  | X
24 | Buildings | CIIC | Northern Building Improvements | Manihiki Tauhunu School Upgrades |  | Upgrade |  | Manihiki | 300 | CIG | [6 empty] | X |  |  |  | X
25 | Buildings | ICI | Pa Enua Cyclone Shelter Program | Nassau Cyclone Shelter | Stand alone cyclone shelter for public | New |  | Nassau | 2000 | CIG | P1 |  | X |  |  | X | X |  |  |  | X | X | [6 empty] | To be scoped and designed
26 | Buildings | CIIC | Rarotonga Buildings Program | National Stadium |  | Upgrade |  | Cook Islands | 4000 | [5 empty] | X | X | X |  | X | X | X | X
27 | Buildings | MOH | Rarotonga Buildings Program | New Prison | Review of the entire prison complex and reconstruction of the Master Plan | New |  | Cook Islands | 6000 | [6 empty] | X | X | [10 empty] | X
28 | Buildings | ICI | Pa Enua Cyclone Shelter Program | Penrhyn Cyclone Shelter | Stand alone cyclone shelter for public | New | ON | Penrhyn | 500 | CIG | P2 |  | X |  |  | X | X |  | X | [9 empty] | Tender accepted and under construction
29 | Buildings | CIIC | Rarotonga Buildings Program | QR Residence | Permanent Residence For Head Of State | New |  | Cook Islands | 1000 | [6 empty] | X | X |  |  | X | X
30 | Buildings | ICI | Pa Enua Cyclone Shelter Program | Rakahanga Cyclone Shelter | Stand alone cyclone shelter for public | New |  | Rakahanga | 2050 | CIG | P1 |  | X |  |  | X | X |  |  | X | X | [7 empty] | To be scoped and designed
31 | Buildings | CIIC | Northern Building Improvements | Rakahanga Island Admin and Government Offices |  | New |  | Rakahanga | 300 | CIG | [6 empty] | X |  | X
32 | Buildings | CIIC | Northern Building Improvements | Rakahanga New Hospital Roof |  | Upgrade |  | Rakahanga | 300 | CIG | [6 empty] | X |  |  | X
33 | Buildings | CIIC | Northern Building Improvements | Rakahanga School Upgrades |  | Upgrade |  | Rakahanga | 300 | CIG | [6 empty] | X |  |  |  | X
34 | Buildings | ICI | Rarotonga Cyclone Shelter Program | Rarotonga Cyclone Shelter Upgrade | Renovating the deficient shelters on Rarotonga | New |  | Rarotonga | 30000 |  | P1 | Cat.5 | X |  |  | X | X |  |  |  | X | X | X | X | X
35 | Buildings | CIIC | Rarotonga Government Buildings | Te Atukura Parliament and Ministerial Offices | New Parliament & Ministerial Offices | New |  | Cook Islands | 10000 |  |  | Cat.4 |  |  | X | X | X | [10 empty] | X
36 | Buildings | CIIC | Rarotonga Government Buildings | Vaikapuangi Government Office Complex | All encompassing Gvt building proposal downtown | New |  | Cook Islands | 56000 |  |  | Cat.5 |  |  | X | X | X |  | X | [6 empty] | X | X | X | Prelim design complete, will need to be staged.
37 | Coastal | ICI | National Coastal Protection Program | Aroa Stream Embankment | Upgrade of stormwater system part of island wide Pro | Upgrade |  | Rarotonga | 500 | CIG |  |  | X |  |  |  | X |  | X | [9 empty] | To be scoped and designed
38 | Coastal | ICI | National Coastal Protection Program | Avana Coastal Protection | Small CCAF project started - to be extended. | Upgrade |  | Rarotonga | 10000 |  |  |  | X |  |  | X | X |  |  | X | [8 empty] | To be scoped and designed
39 | Coastal | ICI | National Coastal Protection Program | Coastal Management and Mitigation | Critcal zones around island to be scoped and designed | Study |  | Rarotonga | 10000 |  |  |  | X |  | X | X |  |  | X | X | X | X | [6 empty] | To be scoped and designed
40 | Coastal | CIIC | Rarotonga Township Enhancements | Coastal Prominade and Town Centre Enhancements |  | New |  | Rarotonga | 2000 | [6 empty] | X | X |  |  |  |  | X | X
41 | Coastal | ICI | National Coastal Protection Program | Northern Coastal Erosion and Protection | Various island requirements | Upgrade |  | Northern | 8000 | GCF |  |  | X |  |  | X | X |  |  |  | X | X | X | [5 empty] | To be scoped and designed
42 | Coastal | ICI | National Coastal Protection Program | Pa Enua Coastal Erosion Protection | Assessment and construction | Study |  | Cook Islands | 1200 |  |  |  | X |  | X | X | X |  |  | X | X | X | [6 empty] | To be scoped and designed
43 | Coastal | ICI | National Coastal Protection Program | Pukapuka Causeway Protection | Upgrade of causeway road due to higher sea activity | Upgrade |  | Pukapuka | 1000 |  | P1 |  | X |  |  | X | X |  |  |  | X | [7 empty] | Needs FS update
44 | Coastal | ICI | National Coastal Protection Program | Pukapuka Cyclone Shelter Access Road | To provide a suitable vehicle access to shelter | Upgrade | CO | Pukapuka | 500 |  | P1 |  | X |  |  | X | X |  |  |  | X | [7 empty] | Should sit with above
45 | Education | MOE | National Tertiary Campus Improvements | Education Infrastructure Master Plan |  | Study |  | Cook Islands | 200 | [5 empty] | X |  |  |  |  | X
46 | Education | CIIC | Rarotonga Education Infrastructure Program | Tereora College Redevelopment Stages 2 and 3 | Stage 2 upgrade of the academic learning centres. Stage 3 Princess Anne Hall upgrades for the Facaulty of Arts | Upgrade |  | Rarotonga | 24000 |  |  | Cat.4 |  |  |  | X | X | [5 empty] | X | X | X | X
47 | Education | CIIC | Rarotonga Education Infrastructure Program | Tereora Pa Enua Hostel | Hostel for the Pa Enua students | New |  | Rarotonga | 1000 | [6 empty] | X | X |  |  | X | X
48 | Education | MFEM | National Tertiary Campus Improvements | USP Campus Construction | Campus, dorm and faculty housing (Scoping study to confirm) | New |  | Cook Islands | 12500 | [5 empty] | X | X | X |  | X |  | X | X | X | [5 empty] | Will require detailed design, and construction
49 | Energy | TAU | Rarotonga Energy Upgrades | 6MW PV Generation Contract |  | Upgrade |  | Rarotonga |  |  | P2 | Cat.4 |  |  |  | X | X
50 | Energy | TMU | Aitutaki Renewable Energy Program | Aitutaki Solar Stage 2 | Scoping and Implementation | Upgrade |  | Aitutaki | 7000 |  |  | Cat.4 | X |  |  | X | X |  |  |  | X | X
51 | Energy | TAU | Rarotonga Energy Upgrades | Energy Production/Distribution Upgrade |  | Upgrade |  | Rarotonga | 0 |  |  | Cat.4 |  |  |  | X | X
52 | Energy | TAU | Rarotonga Energy Upgrades | Network Stage 2 |  | Upgrade |  | Rarotonga | 10000 |  |  | Cat.4 |  |  |  | X | X | X | X | X | X | X | X | X | X | X | X
53 | Energy | TAU | Northern Renewable Energy Program | Northern Battery Replacement & Upgrades |  | Renew |  | Northern | 5000 |  | P2 |  | X |  |  |  | X |  |  | X | X | X
54 | Energy | TAU | Rarotonga Energy Upgrades | Private Sector Generation | Feasibility? Maybe scrapped | Study |  | Rarotonga | 0 |  |  | Cat.4 |  |  | X | [13 empty] | Private funded power scheme
55 | Energy | TAU | Rarotonga Energy Upgrades | Renewable Energy Project Management |  | New |  | Rarotonga | 0 |  |  | Cat.4 | X |  |  | X | X
56 | Energy | TAU | Rarotonga Energy Upgrades | TAU Generation Projects |  | Upgrade |  | Rarotonga | 21000 |  |  | Cat.4 |  |  |  | X | X | X | X | X | X | X | X | X | X | X | X
57 | Energy | TAU | Rarotonga Energy Upgrades | Upgrade Existing Grid and Equipment |  | Upgrade |  | Rarotonga | 5067 |  |  | Cat.4 |  |  |  | X | X | X | X | X | X | X | X | X | X | X | X
58 | Health | INTAFF | National Health Infrastructure Program | Aged Care Facility |  | New |  | Cook Islands | 4250 | ADB |  |  |  |  | X | X | X |  | X | X | X | X
59 | Health | MOH | National Health Infrastructure Program | Mental Health Facility |  | New |  | Cook Islands | 900 | CIG | P1 |  |  |  | X | X | X |  | X
60 | Health | MOH | National Health Infrastructure Program | New Rarotonga Hospital |  | New |  | Rarotonga | 60000 |  |  | Cat.5 |  |  | X | X | X |  |  | X | X | X | X | X | X | X
61 | Health | MOH | National Health Infrastructure Program | TMO - Primary Care Centre of Excellence | Construction of a Primary Care and Pandemic Centre at Tupapa to replace the sub standard health facillity and infrastructure. | Upgrade |  | Rarotonga | 11000 | [5 empty] | X | X | X |  |  |  |  | X | X
62 | ICT | OPM |  | ICT Server Room, Network Upgrade |  | New |  | Cook Islands | 1700 | CIG | P2 |  |  |  |  | X | X |  | X
63 | ICT | ACL | Southern ICT Connectivity | Southern Submarine Fibre Optic Cable | Submarine fibre-optic cable connecting of the Sth Cooks | New |  | Southern | 10000 |  |  | Cat.4 |  |  | X | X | X | [10 empty] | X
64 | Marine | CIPA | Aitutaki Harbour and Marina Improvements | Aitutaki (Orongo) Marina Improvements | Marina upgrade, passage dredging and town centre dev | Upgrade |  | Aitutaki | 13000 |  |  | Cat.4 |  |  |  | X | X
65 | Marine | CIPA | Aitutaki Harbour and Marina Improvements | Aitutaki Harbour Passage Dredging |  | Renew |  | Aitutaki | 1800 | CIG | P2 | [5 empty] | X | X | [10 empty] | New Dredge about to be received.
66 | Marine | ICI | Southern Harbour Improvements | Atiu Wharf Upgrade |  | Upgrade |  | Atiu | 1500 | [6 empty] | X | X |  |  |  | X
67 | Marine | CIPA | Rarotonga Harbour Improvements | Avatiu Harbour Entrance Widening |  | Upgrade |  | Rarotonga | 1000 | [6 empty] | X | X | [6 empty] | X
68 | Marine | CIPA | Rarotonga Harbour Improvements | Avatiu Eastern Breakwater |  | Renew |  | Rarotonga | 1000 | [6 empty] | X | X | [7 empty] | X
69 | Marine | CIPA | Rarotonga Harbour Improvements | Avatiu Western Marina Extension | Including cyclone protection works | Upgrade |  | Rarotonga | 4000 |  |  |  | X |  |  | X | X | [6 empty] | X | X
70 | Marine | ICI | Southern Harbour Improvements | Mangaia Harbour Climate Resilience |  | Upgrade | ON | Mangaia | 985 | CIG | P2 |  |  |  |  | X | X
71 | Marine | ICI | Northern Harbour Improvements | Manihiki Jetty Construction |  | New |  | Manihiki | 360 | [6 empty] | X | X |  |  |  | X
72 | Marine | ICI | Southern Harbour Improvements | Mauke Harbour Upgrade |  | Upgrade |  | Mauke | 360 | [6 empty] | X | X |  | X
73 | Marine | ICI | Southern Harbour Improvements | Mitiaro Wharf Upgrade |  | Upgrade |  | Mitiaro | 500 | [6 empty] | X | X |  | X
74 | Marine | ICI | Northern Harbour Improvements | Nassau Harbour Improvements | Design and construction | Upgrade |  | Nassau | 4650 |  | P2 |  |  |  |  | X | X |  |  | X | [8 empty] | Scping and survey recenty carried out
75 | Marine | ICI | Rarotonga Harbour Improvements | National Harbours Road Map |  | Study |  | Cook Islands | 300 |  | P2 |  |  |  | X |  |  |  | X
76 | Marine | ICI | Northern Harbour Improvements | Penrhyn (TeTautua & Omoka) Port Facilities | Jetty construction for separate villages | Upgrade |  | Penrhyn | 1000 | CIG | [5 empty] | X | X |  |  | X
77 | Marine | ICI | Northern Harbour Improvements | Penrhyn Harbour Assessment | Feasibility study for main island facility and potential for export fish offloading | Study |  | Penrhyn | 250 |  | P2 |  |  |  | X |  |  |  | X | [9 empty] | Awaiting feasibility study for costs
78 | Marine | ICI | Northern Harbour Improvements | Penrhyn Harbour Upgrade | Upgraded harbour and protection works for relocated fuel depot | Upgrade |  | Penrhyn | 20000 | [6 empty] | X | X |  |  |  |  | X | X
79 | Marine | ICI | Pukapuka Harbour Improvements | Pukapuka Harbour Upgrade |  | Upgrade |  | Pukapuka | 4000 | [6 empty] | X | X |  |  |  | X
80 | Marine | ICI | Pukapuka Harbour Improvements | Pukapuka Jetty Development |  | Upgrade |  | Pukapuka | 360 | [6 empty] | X | X |  |  |  | X
81 | Marine | ICI | Northern Harbour Improvements | Rakahanga Harbour Improvement |  | Study |  | Rakahanga | 120 |  | P2 |  |  |  | X |  |  |  | X
82 | Marine | MFEM | National Vessel Program | The National Boat | Development of a purpose built boat to service the Cook Islands | New |  | Cook Islands | 10000 | [5 empty] | X | X | X |  |  |  |  | X | X |  |  |  |  | X
83 | Municipal | CIIC | Rarotonga Township Enhancements | Avatiu Port Walkway and Marina |  | New |  | Rarotonga | 1000 | [6 empty] | X | X |  |  |  |  | X | X
84 | Municipal | CIIC | Rarotonga Township Enhancements | Markets and Constitution Park Reorganisation |  | New |  | Rarotonga | 2250 | [6 empty] | X | X |  | X | X | X | X
85 | Municipal | CIIC | Rarotonga Township Enhancements | Nikao Social Centre |  | New |  | Rarotonga | 7000 | [6 empty] | X | X | [5 empty] | X | X | X | X
86 | Municipal | ICI | Rarotonga Township Enhancements | Panama Walk and Cycleway |  | New |  | Rarotonga | 2000 | [6 empty] | X | X | [6 empty] | X | X
87 | Municipal | ICI | Rarotonga Township Enhancements | Two Roads Parking, Lighting and Footpaths |  | New |  | Rarotonga | 2000 | [6 empty] | X | X | [5 empty] | X | X
88 | Road | ICI | Rarotonga Road Improvements | Aroko Road Widening Project | Increase road width for safety | Upgrade | CO | Rarotonga | 750 | [6 empty] | X | X |  | X | [9 empty] | Awaiting completion of Drainage Works
89 | Road | ICI | Rarotonga Road Improvements | Arorangi Drainage Improvements | Drain/Culvert upgrades to cater for more intense rain. | Study | PI | Rarotonga | 1060 |  | P2 |  |  |  | X |  |  |  | X | [9 empty] | Should follow Muri drainage improvements
90 | Road | ICI | Rarotonga Road Improvements | Culvert Replacement & Improvement | Rarotonga wide renewal of culverts | Upgrade | PI | Rarotonga | 1000 | [6 empty] | X | X |  |  |  | X | X | [6 empty] | Ditto
91 | Road | ICI | Rarotonga Bridge Renewals | Empire Bridge Replacement | Required due to safety issues | Renew | CO | Rarotonga | 3600 |  | P1 |  | X |  |  | X | X |  | X | X | [8 empty] | Advertised for tenders Feb 2021
92 | Road | ICI | Southern Road Improvement Program | Mangaia Road Upgrades | Fixing the main artery through Mangaia | Upgrade |  | Mangaia | 3000 |  | P1 |  |  |  |  | X | X |  |  | X
93 | Road | ICI | Southern Road Improvement Program | Mauke Road Resurfacing and Rehabilitation | Resurfacing and rehabilitation | Renew |  | Mauke | 1200 | [6 empty] | X | X |  | X
94 | Road | ICI | Rarotonga Bridge Renewals | Miscellaneous Bridge Upgrades |  | Renew |  | Rarotonga | 8300 |  | P2 |  | X |  |  | X | X | [5 empty] | X | X | X | X | X
95 | Road | ICI | Southern Road Improvement Program | Mitiaro Road Resurfacing and Rehabilitation | Resurfacing and rehabilitation | Renew |  | Mitiaro | 800 | [6 empty] | X | X |  | X | X
96 | Road | ICI | Rarotonga Road Improvements | Muri Area Upgrade with Footpaths | Kerb & Channel & Footpaths proposed on sea side | Upgrade | PI | Rarotonga | 1500 | [6 empty] | X | X |  |  |  | X | [7 empty] | New project in high tourist area
97 | Road | ICI | Rarotonga Road Improvements | Road Safety Improvements | Signage, guard railing etc | Upgrade | PI | Rarotonga | 1102 | [6 empty] | X | X |  | X | X | X | X | [6 empty] | Ongoing
98 | Road | ICI | Rarotonga Road Reconstruction Program | Roads Planned Periodic Maintenance | Resurfacing and rehabilitation | Renew | PI | Rarotonga | 18800 | [6 empty] | X | X |  | X | X | X | X | [6 empty] | Ongoing
99 | Road | ICI | Rarotonga Bridge Renewals | Sheraton Bridge Replacement | Design and construction | Renew | CO | Rarotonga | 3300 |  | P1 |  | X |  |  | X | X |  |  | X | X | [7 empty] | Decision around location to be resolved.
100 | Road | ICI | Rarotonga Bridge Renewals | Taipara Bridge Replacement |  | Renew |  | Rarotonga | 3300 |  | P1 |  | X |  |  | X | X |  |  |  | X | X
101 | Sanitation | ICI | Southern Sanitation Improvements | Aitutaki Sanitation Upgrades | TBD - Must look at options for desludging septic | Upgrade |  | Aitutaki | 3000 | CIG | P2 |  |  |  |  | X | X |  |  |  | X | X
102 | Sanitation | MFEM | Rarotonga Sanitation Improvements | MTVKTV Long-term Sanitation Upgrades | Reticulated system for Rarotonga wih start in Muri area. | Upgrade |  | Rarotonga | 50000 | NZAID | P2 | Cat.5 |  |  |  | X | X | [5 empty] | X | X | X | X | X | X | GHD consultants have ben scoping possibilities
103 | Sanitation | ICI | Northern Sanitation Improvements | Northern Sanitation Upgrades |  | Renew |  | Northern | 2200 | [5 empty] | X | X | X |  |  | X |  |  |  | X | X |  |  |  | Combine with Sth Group
104 | Sanitation | MOH | Northern Sanitation Improvements | Pukapuka Household Sanitation Facilities |  | New |  | Pukapuka | 970 | CIG | P1 | [5 empty] | X |  | X
105 | Sanitation | ICI | Rarotonga Sanitation Improvements | Sanitation Management Study | Feasibility study (Pa Enua and Rarotonga) | Study |  | Cook Islands | 160 | CIG |  |  |  |  | X |  |  |  | X
106 | Sanitation | ICI | Southern Sanitation Improvements | Southern Sanitation Upgrades | Subject to the Scoping Study | Renew |  | Southern | 2150 | [5 empty] | X | X | X |  |  | X |  |  |  | X | X
107 | Sanitation | ICI | Rarotonga Sanitation Improvements | Tepuka Sanitation Improvement | Upgrade of current treatment and discharge system. | Upgrade |  | Rarotonga | 5000 | CIG | P2 | Cat.4 |  |  |  | X | X |  | X | X | X | [7 empty] | Heavy populated area close by schools.
108 | Waste | ICI | Rarotonga Solid Waste Management Program | Hazardous Waste Handling Facilities | Feasibility / design study required | Study |  | Rarotonga | 100 |  | P1 |  |  |  | X |  |  |  | X | [9 empty] | Part of overall waste management strategy
109 | Waste | ICI | Rarotonga Solid Waste Management Program | Nation Waste Management Strategy | Scoping Options and feasibility | Study |  | Rarotonga | 500 |  | P1 |  |  |  | X |  |  |  | X
110 | Waste | ICI | Northern Solid Waste Program | Northern Waste Centres Upgrade |  | Upgrade |  | Northern | 100 | [7 empty] | X
111 | Waste | ICI | Rarotonga Solid Waste Management Program | Recycling Transfer Facility | Feasibility / design study required | Study |  | Rarotonga | 200 |  | P2 |  | X |  | X |  |  |  | X | [9 empty] | Upgrade and extension
112 | Waste | ICI | Rarotonga Solid Waste Management Program | Solid Waste Incinerator | Feasibility and construction | New |  | Rarotonga | 5060 |  | P2 |  | X |  | X | X | X |  |  |  | X | [7 empty] | Needs to be fully scoped and planned.
113 | Waste | ICI | Southern Solid Waste Management Program | Southern Waste Centres Upgrade |  | Upgrade |  | Southern | 200 | [7 empty] | X
114 | Waste | ICI | Rarotonga Solid Waste Management Program | TGA Rarotonga Compost Facilities | Feasibility / design study required | New |  | Rarotonga | 500 |  |  |  | X |  |  | X | X | [11 empty] | Part of overall waste management strategy
115 | Water | ICI | Aitutaki Water Security Program | Aitutaki Domestic Water Tanks | Water tanks to private homes | New | CO | Aitutaki | 500 |  | P2 |  | X |  |  |  | X | X | [10 empty] | 290 homes left to complete
116 | Water | ICI | Aitutaki Water Security Program | Aitutaki Upgrade of Galleries and Reticulation |  | Upgrade |  | Aitutaki | 5200 | CIG |  |  | X |  | X | X | X |  |  | X | X | X
117 | Water | ICI | Aitutaki Water Security Program | Aitutaki Upgrade Reticulation System |  | Upgrade |  | Aitutaki | 5000 |  |  | Cat.4 | X |  |  | X | X |  |  |  | X | X
118 | Water | ICI | Southern Water Security Program | Aitutaki Water Ground Water Study | Following SPC scoping mission in 2020 | Study |  | Aitutaki | 500 |  | P2 |  | X |  | X |  |  |  |  | X
119 | Water | ICI | Southern Water Security Program | Atiu Community Water Storage | Repair of a number of 45,000 lt tanks | New |  | Atiu | 200 |  | P2 |  | X |  |  |  | X |  |  | X | [8 empty] | Funding to be determined
120 | Water | ICI | Southern Water Security Program | Atiu Water Reticulation System | Reticulaton system for Villages (water sourcing required) | New |  | Atiu | 3000 |  | P2 |  |  |  |  | X | X |  |  | X | X | [7 empty] | To be fuly scoped for gound water source
121 | Water | TTV | Rarotonga Water Security Program | CCTV Mapping of Network & Pipe Cleaning | Confirm network and cleaning procedure | New |  | Rarotonga | 581 | CIG | P2 | Cat.5 |  |  |  | X | X | X | X | [9 empty] | Required to ensure potable water to customers
122 | Water | ICI | Southern Water Security Program | Mangaia Water Distribution Upgrade | Oneroa Village supply upgrade | Upgrade |  | Mangaia | 1500 | CIG | P2 | [5 empty] | X | X | X | X | [8 empty] | Scoping and Design underway.
123 | Water | ICI | Southern Water Security Program | Mitiaro Water Source and Distribution Improvement | 2km pipeline construction | New |  | Mitiaro | 800 |  | P2 |  | X |  |  | X | X
124 | Water | ICI | Southern Water Security Program | Mitiaro Water Tanks | Continuation of upgrade to community water system. | New |  | Mitiaro | 265 |  | P2 |  | X |  |  |  | X |  |  |  | X | [7 empty] | Scoping and Design underway.
125 | Water | ICI | Northern Water Security Program | Northern Community Water Tanks Rehabilitation | Nth Group tank upgrades need to continue | Renew |  | Northern | 1200 | UNDP/NZ | P2 |  | X |  |  |  | X | X | X | X | [8 empty] | Many completed still others need repairs.
126 | Water | TTV | Rarotonga Water Security Program | Piping To Fix Deadlegs | Many deadlegs need to be eliminated or renewed | New |  | Rarotonga | 1500 | CIG | P2 | Cat.5 |  |  |  |  | X |  | X | [9 empty] | A must as part of process towards potable water
127 | Water | ICI | Northern Water Security Program | Pukapuka Water Gallery Improvement | Gallery Upgrade required | Upgrade |  | Pukapuka | 120 | CIG | P2 |  | X |  |  |  | X |  |  |  | X | [7 empty] | I Council do not want underground water taped.
128 | Water | TTV | Rarotonga Water Security Program | Repairs to Mains | Continual replacement of stage 1 faulty system | New |  | Rarotonga | 30000 | CIG | P2 | Cat.5 |  |  |  |  | X |  | X | X | X | X | X | X | X | X
129 | Water | TTV | Rarotonga Water Security Program | Reservoir & Tank Meters for Turbidity | Meters at intake sites that were missing from TMV. | New |  | Rarotonga | 200 | CIG | P2 | Cat.5 |  |  |  |  | X | X | X | X | [8 empty] | Part of getting TTV into full quality mode
130 | Water | TTV | Rarotonga Water Security Program | SCADA Installation | Supervisory Control and Data Acquisition | New |  | Rarotonga | 1850 | CIG | P2 | Cat.5 |  |  |  | X | X | X | X | X |  | X | [6 empty] | Using IT monitoring and control of site systems.
131 | Water | TTV | Rarotonga Water Security Program | Sludge Disposal | Land and facilities required for sludge disposal | New |  | Rarotonga | 200 | CIG | P2 | Cat.5 |  |  | X | X | X | X | X | [9 empty] | Suitable land identified. Requires EIA
132 | Water | ICI | Southern Water Security Program | Southern Water Ground Water | Developing Reticulated systems in Mitiaro & Mangaia | New |  | Southern | 1600 |  | P2 |  | X |  | X | X | X |  |  | X | X | X | X
133 | Water | TTV | Rarotonga Water Security Program | Sub Main Replacement Sector 5 - Titikaveka | Replacement AC sub mains back road Titikaveka | New |  | Rarotonga | 3366 | CIG | P2 | Cat.5 |  |  |  | X | X | X | X | X | X | X | [6 empty] | High priority to reduce pipe losses.
134 | Water | TTV | Rarotonga Water Security Program | UV Station Maintenance Testing & New School UV's | Continual UV maintenance and new school unit instal | New |  | Rarotonga | 373.6 | CIG |  | Cat.5 |  |  |  | X | X | X | [10 empty] | Provides potable water to general public
135 | Water | TTV | Rarotonga Water Security Program | Water Meters - Purchase and Install | Installation of water meters to all connections | New |  | Rarotonga | 8000 | CIG |  | Cat.5 | X |  |  | X | X | X | X | X | X | X | [6 empty] | Needs to be in place before any charging !!!
136 | Water | TTV | Rarotonga Water Security Program | Water Network Infrastructure/Laboratory Assets | Facilities req to check filter & water Quality | New |  | Rarotonga | 100 | CIG | P2 | Cat.5 |  |  |  | X | X | X | X | [9 empty] | Part of getting TTV into full quality mode
687069.6

## Prioritisation
[6 empty] | SCALE |  |  |  | BENEFIT
|  |  | #Cat.4 & 5 Complexity Projects | Major Program | Core Program | Cost | Complexity | Sustainability | Scale Score | Scope | Economic Impact | Environmental Impact | Social Impact | Benefit Score | 80%Benefit-20%Scale | Ranking | Project Scale Criteria |  | Project Benefits Criteria
ID | Program | Budget ($million) |  |  |  | 30% | 35% | 35% | 20% | 25% | 30% | 25% | 20% | 80% |  |  | Cost |  | Scope
22 | Rarotonga Education Infrastructure Program | 25 | 1 | X |  | 4 | 4 | 4 | 4 | 5 | 4 | 3 | 5 | 4.2 | 2.56 | 2 | 1 | <=$400k | 1 | Target population is less than 500.
28 | Rarotonga Sanitation Improvements | 55 | 2 | X |  | 4 | 5 | 5 | 4.7 | 4 | 4 | 5 | 4 | 4.25 | 2.46 | 3 | 2 | >400k and <=5m | 2 | The activity impacts between 500-1,500 people.
3 | Aitutaki Renewable Energy Program | 7 | 1 | X |  | 3 | 4 | 5 | 4.05 | 3 | 4 | 4 | 4 | 3.75 | 2.19 | 6 | 3 | >5m and <=15m | 3 | The activity impacts 1,500-2,500 people.
6 | National Health Infrastructure Program | 76.2 | 1 | X |  | 5 | 5 | 4 | 4.65 | 5 | 3 | 3 | 5 | 3.9 | 2.19 | 6 | 4 | >$15m and <=$40m | 4 | Impacts 1,500-10,000 OR a target population such as women, children, the elderly, disabled, or other disadvantaged groups.
18 | Rarotonga Airport Upgrades | 67.1 | 0 | X |  | 5 | 4 | 4 | 4.3 | 4 | 4 | 3 | 4 | 3.75 | 2.14 | 10 | 5 | >$40million | 5 | Nationwide impacts
24 | Rarotonga Government Buildings | 66 | 2 | X |  | 4 | 4 | 5 | 4.35 | 4 | 3 | 4 | 4 | 3.7 | 2.09 | 11 | Complexity |  | Economic Risk/Benefit
23 | Rarotonga Energy Upgrades | 36.1 | 7 | X |  | 4 | 5 | 5 | 4.7 | 4 | 3 | 4 | 4 | 3.7 | 2.02 | 12 | 1 | The activity can be easily implemented within the year with little or no additional inputs | -3 | Significant upfront costs as well as sustained ongoing expenses with no recourse for cost recovery.
29 | Rarotonga Solid Waste Management Program | 6.4 | 0 | X |  | 5 | 5 | 5 | 5 | 4 | 3 | 5 | 3 | 3.75 | 2 | 13 | 2 | Requires short term TA (within the year) but little recurring assistance | -2 | Upfront costs and sustained ongoing expenses, with some cost recovery.
7 | National Tertiary Campus Improvements | 12.7 | 0 | X |  | 3 | 4 | 5 | 4.05 | 4 | 3 | 3 | 4 | 3.45 | 1.95 | 15 | 3 | The activity will require expertise and TA over a two year period. | -1 | One off upfront cost plus repairs and maintenance, little or no cost recovery.
9 | Northern Airport Improvements | 19.7 | 0 | X |  | 4 | 4 | 4 | 4 | 3 | 3 | 3 | 4 | 3.2 | 1.76 | 23 | 4 | Multi year activity with up to 2 permanent staff added. | 0 | One off upfront cost, little or no cost recovery.
32 | Southern Airport Improvements | 13.4 | 0 | X |  | 4 | 4 | 4 | 4 | 4 | 3 | 2 | 4 | 3.2 | 1.76 | 23 | 5 | Multi year activity, permanent staff added, and multiple contracts and/or project management unit required. | 1 | One off negative cost, minimal cost recovery.
30 | Rarotonga Township Enhancements | 16.3 | 0 | X |  | 5 | 5 | 4 | 4.65 | 4 | 1 | 5 | 3 | 3.15 | 1.59 | 32 | Sustainability |  | 2 | Cost neutral, most costs can be recovered.
25 | Rarotonga Harbour Improvements | 6.3 | 0 | X |  | 3 | 4 | 5 | 4.05 | 4 | 3 | 1 | 4 | 2.95 | 1.55 | 33 | 1 | No recurring impacts beyond the financial year. | 3 | Positive return on investment but less than commercial rate
31 | Rarotonga Water Security Program | 46.2 | 10 | X |  | 4 | 5 | 5 | 4.7 | 4 | 1 | 3 | 5 | 3.05 | 1.5 | 34 | 2 | There is an additional workload that can be taken by current capacity or a small increase in opex (i.e. less than 20% of agency opex up to 2 yrs) | 4 | The return on investment will result in a commercial rate of return.
16 | Pa Enua Cyclone Shelter Program | 4.9 | 0 |  | X | 2 | 3 | 2 | 2.35 | 4 | 3 | 4 | 5 | 3.9 | 2.65 | 1 | 3 | There is a need to recruit additional resources, between 20% - 50 % of agency’s operating budget for up to 3 years. | 5 | Will result in an increase of more than 2% of GDP.
27 | Rarotonga Road Reconstruction Program | 18.8 | 0 |  | X | 4 | 2 | 3 | 2.95 | 4 | 4 | 2 | 4 | 3.5 | 2.21 | 4 | 4 | Requires foreign TA and has ongoing budgetary implications beyond what is currently allocated. | Environmental Risk/Benefit
17 | Pukapuka Harbour Improvements | 4.4 | 0 |  | X | 2 | 2 | 2 | 2 | 2 | 4 | 3 | 4 | 3.25 | 2.2 | 5 | 5 | High TA component, large cost, and will result in significant, long lasting change. | -5 | Severe wide spread negative impact, irreversable
11 | Northern Harbour Improvements | 26.4 | 0 |  | X | 4 | 3 | 4 | 3.65 | 3 | 5 | 3 | 3 | 3.6 | 2.15 | 8 |  |  | -4 | Severe negative impact, irreversible
5 | National Coastal Protection Program | 31 | 0 |  | X | 3 | 4 | 4 | 3.7 | 5 | 2 | 3 | 5 | 3.6 | 2.14 | 9 |  |  | -3 | Severe negative impact, generational recovery period
38 | Southern Water Security Program | 7.9 | 0 |  | X | 1 | 3 | 3 | 2.4 | 4 | 1 | 3 | 5 | 3.05 | 1.96 | 14 |  |  | -2 | Severe negative impact, significant time and cost to rehabilitate
20 | Rarotonga Buildings Program | 11 | 0 |  | X | 3 | 2 | 3 | 2.65 | 4 | 1 | 4 | 4 | 3.1 | 1.95 | 15 |  |  | -1 | Severe negative impact
14 | Northern Solid Waste Program | 0.1 | 0 |  | X | 1 | 3 | 4 | 2.75 | 3 | 1 | 5 | 4 | 3.1 | 1.93 | 17 |  |  | 1 | Moderate negative impact
21 | Rarotonga Cyclone Shelter Program | 30.3 | 2 |  | X | 3 | 3 | 2 | 2.65 | 4 | 1 | 3 | 5 | 3.05 | 1.91 | 18 |  |  | 2 | Mild negative impact
15 | Northern Water Security Program | 1.3 | 0 |  | X | 2 | 3 | 3 | 2.7 | 4 | 1 | 3 | 5 | 3.05 | 1.9 | 19 |  |  | 3 | Neutral environmental risks/benefits
2 | Aitutaki Harbour and Marina Improvements | 14.8 | 1 |  | X | 4 | 4 | 3 | 3.65 | 3 | 4 | 2 | 4 | 3.25 | 1.87 | 20 |  |  | 4 | Indirect benefits that improve environment
37 | Southern Solid Waste Management Program | 0.2 | 0 |  | X | 3 | 3 | 4 | 3.35 | 4 | 1 | 5 | 3 | 3.15 | 1.85 | 21 |  |  | 5 | Significant improvement of environment or risk mitigation/increased resilience to climate change impacts.
1 | Aitutaki Airport Improvements | 3.2 | 0 |  | X | 2 | 3 | 4 | 3.05 | 3 | 3 | 3 | 3 | 3 | 1.79 | 22 |  |  | Social Risk/Benefit
19 | Rarotonga Bridge Renewals | 18.5 | 0 |  | X | 4 | 2 | 2 | 2.6 | 4 | 1 | 3 | 4 | 2.85 | 1.76 | 25 |  |  | -5 | Severe negative national impact, irreversible
33 | Southern Harbour Improvements | 3.3 | 0 |  | X | 2 | 3 | 4 | 3.05 | 4 | 2 | 3 | 3 | 2.95 | 1.75 | 26 |  |  | -4 | Severe negative generational impacts
8 | National Vessel Program | 10 | 0 |  | X | 3 | 3 | 3 | 3 | 4 | 2 | 2 | 4 | 2.9 | 1.72 | 27 |  |  | -3 | Severe negative impact, over the long term (10+ years)
4 | Aitutaki Water Security Program | 10.7 | 1 |  | X | 3 | 4 | 4 | 3.7 | 3 | 1 | 4 | 5 | 3.05 | 1.7 | 28 |  |  | -2 | Severe negative impact, over the mid term (5 years +)
35 | Southern Road Improvement Program | 5 | 0 |  | X | 3 | 3 | 3 | 3 | 4 | 1 | 3 | 4 | 2.85 | 1.68 | 29 |  |  | -1 | Severe negative impact, localised or temporary
12 | Northern Renewable Energy Program | 5 | 0 |  | X | 2 | 5 | 4 | 3.75 | 3 | 2 | 4 | 3 | 2.95 | 1.61 | 31 |  |  | 1 | Moderate negative impact
36 | Southern Sanitation Improvements | 5.3 | 0 |  |  | 2 | 3 | 3 | 2.7 | 4 | -1 | 5 | 4 | 2.75 | 1.66 | 30 |  |  | 2 | Mild negative impact
13 | Northern Sanitation Improvements | 3.2 | 0 |  |  | 2 | 3 | 3 | 2.7 | 3 | -1 | 5 | 4 | 2.5 | 1.46 | 35 |  |  | 3 | Neutral social risks/benefits
10 | Northern Building Improvements | 1.5 | 0 |  |  | 2 | 2 | 3 | 2.35 | 3 | 1 | 3 | 3 | 2.4 | 1.45 | 36 |  |  | 4 | Indirect benefits that improve or save lives.
26 | Rarotonga Road Improvements | 5.4 | 0 |  |  | 3 | 3 | 3 | 3 | 4 | 1 | 2 | 3 | 2.4 | 1.32 | 37 |  |  | 5 | Significant improvement of lifestyle or risk mitigation/improvements for disadvantaged groups.
34 | Southern ICT Connectivity | 11.7 | 1 |  |  | 3 | 4 | 5 | 4.05 | 3 | 1 | 3 | 4 | 2.6 | 1.27 | 38
|  | 687.3 | 29

## Codes
Sector Code |  | Project Scale Criteria |  | Project Benefits Criteria
Air | AIR TRANSPORT | Criteria Ratings |  | Scope
Buildings | BUILDINGS AND FACILITIES | Cost |  | 1 | Target population is less than 500.
Coastal | COASTAL PROTECTION | 1 | $10,000 or less | 2 | The activity impacts between 500-1,500 people.
Education | EDUCATION | 2 | $10,000-$50,000 | 3 | The activity impacts 1500-2,500 people.
Energy | ENERGY | 3 | $50,000-$150,000 | 4 | Impacts 1,500-10,000 OR a target population such as women, children, the elderly, disabled, or other disadvantaged groups.
Health | HEALTH | 4 | $150,000-$500,000 | 5 | Nationwide impacts
ICT | INFORMATION & COMMUNICATIONS TECHNOLOGY | 5 | Above $500,000 | Economic Risk/Benefit
Marine | MARINE TRANSPORT | Complexity |  | -3 | Significant upfront costs as well as sustained ongoing expenses with no recourse for cost recovery.
Municipal | MUNICIPAL | 1 | The activity can be easily implemented within the year with little or no additional inputs | -2 | Upfront costs and sustained ongoing expenses, with some cost recovery.
Road | ROAD TRANSPORT | 2 | Requires short term TA (within the year) but little recurring assistance | -1 | One off upfront cost plus repairs and maintenance, little or no cost recovery.
Sanitation | SANITATION | 3 | The activity will require expertise and TA over a two year period. | 0 | One off upfront cost, little or no cost recovery.
Waste | SOLID WASTE | 4 | Multi year activity with up to 2 permanent staff added. | 1 | One off negative cost, minimal cost recovery.
Water | WATER SUPPLY | 5 | Multi year activity, permanent staff added, and multiple contracts and/or project management unit required. | 2 | Cost neutral, most costs can be recovered.
|  | Sustainability |  | 3 | Positive return on investment but less than commercial rate
|  | 1 | No recurring impacts beyond the financial year. | 4 | The return on investment will result in a commercial rate of return.
Project Urgency |  | 2 | There is an additional workload that can be taken by current capacity or a small increase in opex (i.e. less than 20% of agency opex up to 2 yrs) | 5 | Will result in an increase of more than 2% of GDP.
HS Risk | Presents a threat to life an Health & safety of citizens | 3 | There is a need to recruit additional resources, between 20% - 50 % of agency’s operating budget for up to 3 years. | Environmental Risk/Benefit
Critical | Important for the island/community viability, needs urgent addressing | 4 | Requires foreign TA and has ongoing budgetary implications beyond what is currently allocated. | -5 | Severe wide spread negative impact, irreversable
Strategic | Required to improve the standard of living in the long term (non urgent) | 5 | High TA component, large cost, and will result in significant, long lasting change. | -4 | Severe negative impact, irreversible
Socio- Econ | Will enhance socio-economic outcomes |  |  | -3 | Severe negative impact, generational recovery period
|  |  |  | -2 | Severe negative impact, significant time and cost to rehabilitate
Lead Agency |  |  |  | -1 | Severe negative impact
AACI | Airport Authority Cook Islands |  |  | 1 | Moderate negative impact
ACL | Avaroa Cable Limited |  |  | 2 | Mild negative impact
CIIC | Cook Islands Investment Corporation |  |  | 3 | Neutral environmental risks/benefits
CIPA | Cook Islands Ports Authority |  |  | 4 | Indirect benefits that improve environment
ICI | Infrastructure Cook Islands |  |  | 5 | Significant improvement of environment or risk mitigation/increased resilience to climate change impacts.
MOE | Ministry of Education |  |  | Social Risk/Benefit
MFEM | Ministry of Finance and Economic Management |  |  | -5 | Severe negative national impact, irreversible
MOH | Ministry of Health |  |  | -4 | Severe negative generational impacts
MOJ | Ministry of Justice |  |  | -3 | Severe negative impact, over the long term (10+ years)
MOP | Ministry of Police |  |  | -2 | Severe negative impact, over the mid term (5 years +)
MOT | Ministry of Transport |  |  | -1 | Severe negative impact, localised or temporary
NES | National Environment Service |  |  | 1 | Moderate negative impact
OPM | Office of the Prime Minister |  |  | 2 | Mild negative impact
OIG | Outer Island Government administrations |  |  | 3 | Neutral social risks/benefits
TAU | Te Aponga Uira (Power company) |  |  | 4 | Indirect benefits that improve or save lives.
TTV | To Tatou Vai |  |  | 5 | Significant improvement of lifestyle or risk mitigation/improvements for disadvantaged groups.
TMU | Aitutaki Power
MOCS | Correctives Services
INTAFF | Internal Affairs
Islands
Aitutaki
Atiu
Cook Islands
Mangaia
Manihiki
Manuae
Mauke
Mitiaro
Nassau
Northern
Palmerston
Penrhyn
Pukapuka
Rakahanga
Rarotonga
Southern
Suwarrow
Takutea
Status
ON | Ongoing
CO | Committed
PI | Pipeline
Project Type
New | Build new infrastruture
Upgrade | Upgrade/Improve existing capacity of expand extent
Renew | Refurbish or replace existing (like with like)
Study | Feasibility study for major infrastructure
Funding
CIG
NZAID
ADB
GCF
AIIB
AusAID
Japan
EU
UNDP
SPREP
SPC
PIFS
TBF
UNDP/NZ

## To Delete (hidden)
Cook Islands National Infrastructure Investment Plan (2021 Release) | [8 empty] | Category |  |  |  | 10-yr Budget
[9 empty] | Criticality | Complexity | Climate | Stimulus | Feasibility | Design | Construct |  |  |  | Estimated Start/Duration
Sector Code | Lead Agency | IMP Agency | Program | Project Name | Brief Description | Project Type | Status | Island | [7 empty] | Best Estimate |  | Funding Source | 20/21 | 21/22 | 22/23 | 23/24 | 24/25 | 25/26 | 26/27 | 27/28 | 28/29 | 29/30 | 30/31 | 31/32 | 32/33 | 34/35 | 35/36 | Notes
Air | AACI | AACI | Aitutaki Airport Improvements | Aitutaki Passenger Terminal Improvements | Extension and full rebuild | Upgrade |  | Aitutaki | [5 empty] | X | X | 1190 | 1200 |  |  |  |  | 0.2 | 1 | [10 empty] | Desirable but maybe not necessary
Air | ICI | ICI | Northern Airport Improvements | Manihiki Upgrade to Regional Turbo Prop Runway | Feasibility study and construction for CAA Part 139 | New |  | Manihiki |  |  |  |  | X | X | X | 6660 | 6660 | CIG | 0.16 | 3.5 | 3 | [12 empty] | Req for design tenders underway Mar 21.
Air | ICI | ICI | Northern Airport Improvements | Penrhyn Airport Runway Upgrade | Detailed design | Upgrade |  | Penrhyn | [5 empty] | X | X | 6500 | 6500 |  |  |  | 6.5 | [12 empty] | Sits with Manihiki ( Pos Aussie Funding )
Air | ICI | ICI | Northern Airport Improvements | Pukapuka Airport Runway Upgrade | Detailed design | Upgrade |  | Pukapuka | [5 empty] | X | X | 6500 | 6500 | [5 empty] | 6.5 | [10 empty] | Consideration at time of Manihiki & Penrhyn ??
Air | AACI | AACI | Rarotonga Airport Upgrades | Eastern End Safety Area | Extend runway to provide 200m runoff zone | Upgrade |  | Rarotonga | C1 |  |  |  |  | X | X | 6000 | 6000 |  |  | 3 | 3 | [12 empty] | Land Purchase underway: Aviation requirement
Air | AACI | AACI | Rarotonga Airport Upgrades | Runway Repairs | Runway slab repairs | Renew | ON | Rarotonga | C1 |  |  |  |  | X | X | 6000 | 6000 | NZ Aid | 3 | 3 | [13 empty] | Replacement Slab Contract has been let.
Air | AACI | AACI | Rarotonga Airport Upgrades | Airport Cyclone Protection Works | Western end airfield protection | New |  | Rarotonga | C2 |  | X |  |  | X | X | 1600 | 0 | [16 empty] | Some funding ex Climate Adaption
Air | AACI | AACI | Rarotonga Airport Upgrades | Airport Arrival Terminal - Phase 2 | Replicate phase 1 building to increase size | Upgrade |  | Rarotonga | [5 empty] | X | X | 10900 | 11000 | [9 empty] | 5 | 6 | [5 empty] | Less aircraft movements could see pro 'sit'
Air | AACI | AACI | Rarotonga Airport Upgrades | Airport Departure Terminal Upgrade | Increase Size | Upgrade |  | Rarotonga | [5 empty] | X | X | 11100 | 11000 | [10 empty] | 5 | 6 |  |  |  |  | Ditto -- Await review Master Plan
Air | AACI | AACI | Rarotonga Airport Upgrades | Code C Apron Expansion | Extension of Apron to accommodate extra aircraft | Upgrade |  | Rarotonga | [5 empty] | X | X | 8500 | 8500 | [12 empty] | 8.5 |  |  |  | Ditto -- Await review Master Plan
Air | AACI | AACI | Rarotonga Airport Upgrades | Airport Relocation of Control Tower | Move Tower to southern side of airport | New |  | Rarotonga | [5 empty] | X | X | 12900 | 13000 | [13 empty] | 1 | 12 | X | A very long term project
Air | AACI | AACI | Rarotonga Airport Upgrades | Airport Master Plan | Business plan and strategy | Study | ON | Rarotonga |  |  |  |  | X |  |  | 760 | 700 | ADB | 0.7 | [14 empty] | Aust Con appointed : Review due to Covid
Air | AACI | AACI | Rarotonga Airport Upgrades | Airport Check-in Upgrade | Redesign rebuild of original area | Upgrade |  | Rarotonga | [5 empty] | X | X | 3700 | 3700 |  |  |  | 1 | 2.7 | [11 empty] | Await review of Master Plan
Air | AACI | AACI | Rarotonga Airport Upgrades | Airport Baggage Makeup Area | Redesign rebuild of original area should sit with above. | Upgrade |  | Rarotonga | [5 empty] | X | X | 5600 | 5600 |  |  |  | 1 | 4.6 | [11 empty] | Await review of Master Plan
Air | ICI | ICI | Southern Airport Improvements | Aitutaki Runway Reclamation | Northern end protection of safety runoff area. | Renew |  | Aitutaki | [5 empty] | X | X | 2000 | 2000 | [6 empty] | 2 | [9 empty] | Avaition Requirement
Air | ICI | ICI | Southern Airport Improvements | Atiu Upgrade to Regional Turbo Prop Runway | Feasibility study and construction for CAA Part 139 | Upgrade |  | Atiu | [5 empty] | X | X | 5460 | 5460 |  |  | 0.16 | 2.5 | 2.8 | [11 empty] | Was high priority in 2015 NIIP !!
Air | ICI | ICI | Southern Airport Improvements | Mangaia Airport Runway Upgrade | Relocate & upgrade runway (feasibility and build) | Upgrade |  | Mangaia | [5 empty] | X | X | 5260 | 5260 |  |  |  |  | 0.16 | 2.5 | 2.6 | [9 empty] | Low Priority
Air | ICI | ICI | Southern Airport Improvements | Mauke Airport Fencing Improvements | Fencing to control roaming animals | Upgrade |  | Mauke | C1 | [5 empty] | X | 150 | 150 |  |  | 0.15 | [13 empty] | A safety isue that should proceed.
Air | ICI | ICI | Southern Airport Improvements | Mauke Airport Improvements | Detailed design | Upgrade |  | Mauke | [5 empty] | X | X | 1360 | 1360 |  |  | 0.16 |  | 1.2 | [11 empty] | Sits with Sth Group feasibility study on airports
Air | ICI | ICI | Southern Airport Improvements | Mitiaro Airport Runway Upgrade | Detailed design | Upgrade |  | Mitiaro | [5 empty] | X | X | 1120 | 1100 |  |  |  | 1.1 | [12 empty] | Sits with Sth Group feasibility study on airports
Buildings | MOH | MOH | Rarotonga Buildings Program | New Prison | Review of the entire prison complex and reconstruction of the Master Plan | New |  | Rarotonga | [5 empty] | X | X | 6000 | 500 | [13 empty] | 0.5 |  | X
Buildings | CIIC | CIIC | Rarotonga Buildings Program | QR Residence | Permanent Residence For Head Of State | New |  | Rarotonga | [5 empty] | X | X | 1000 | 1000 |  |  |  | 0.1 | 0.9
Buildings | CIIC | CIIC | Rarotonga Buildings Program | National Stadium |  | Upgrade |  | Rarotonga |  |  |  |  | X | X | X | 4000 | 4000 |  |  | 0.5 | 2 | 0.5 | 1
Buildings | CIIC | CIIC | Northern Building Improvements | Manihiki New Government Building (Replace MoJ) |  | New |  | Manihiki | [6 empty] | X | 300 | 300 | CIG |  |  | 0.3
Buildings | CIIC | CIIC | Northern Building Improvements | Manihiki Tauhunu School Upgrades |  | Upgrade |  | Manihiki | [6 empty] | X | 300 | 300 | CIG |  |  |  | 0.3
Buildings | CIIC | CIIC | Northern Building Improvements | Rakahanga New Hospital Roof |  | Upgrade |  | Rakahanga | [6 empty] | X | 300 | 300 | CIG |  |  | 0.3
Buildings | CIIC | CIIC | Northern Building Improvements | Rakahanga School Upgrades |  | Upgrade |  | Rakahanga | [6 empty] | X | 300 | 300 | CIG |  |  |  | 0.3
Buildings | CIIC | CIIC | Northern Building Improvements | Rakahanga Island Admin and Government Offices |  | New |  | Rakahanga | [6 empty] | X | 300 | 300 | CIG |  | 0.3
Buildings | CIIC | CIIC | Pa Enua Cyclone Shelter Program | Manihiki Major Renovations to Cyclone Centres |  | Upgrade |  | Manihiki | C2 |  | X |  |  |  | X | 300 | 300 | CIG |  | 0.3
Buildings | ICI | ICI | Pa Enua Cyclone Shelter Program | Nassau Cyclone Shelter | Stand alone cyclone shelter for public | New |  | Nassau | C1 |  | X |  |  | X | X | 2000 | 2000 | CIG |  |  |  | 1.8 | 0.2 | [10 empty] | To be scoped and designed
Buildings | ICI | ICI | Pa Enua Cyclone Shelter Program | Penrhyn Cyclone Shelter | Stand alone cyclone shelter for public | New | ON | Penrhyn | C2 |  | X |  |  | X | X | 500 | 500 | CIG |  | 0.5 | [13 empty] | Tender accepted and under construction
Buildings | ICI | ICI | Pa Enua Cyclone Shelter Program | Rakahanga Cyclone Shelter | Stand alone cyclone shelter for public | New |  | Rakahanga | C1 |  | X |  |  | X | X | 2050 | 2100 | CIG |  |  | 1.9 | 0.2 | [11 empty] | To be scoped and designed
Buildings | ICI | ICI | Rarotonga Cyclone Shelter Program | Cyclone Shelters Structural Review | Pa Enua and Rarotonga - Research and Investigations | Study |  | Cook Islands | C1 | Cat.5 | X |  | X |  |  | 300 | 300 | CIG |  | 0.1 | 0.2 | [12 empty] | To be scoped and designed
Buildings | ICI | ICI | Rarotonga Cyclone Shelter Program | Rarotonga Cyclone Shelter Upgrade | Renovating the deficient shelters on Rarotonga | New |  | Rarotonga | C1 | Cat.5 | X |  |  | X | X | 30000 | 30000 |  |  |  |  | 6 | 6 | 6 | 6 | 6
Buildings | CIIC | CIIC | Rarotonga Government Buildings | Te Atukura Parliament and Ministerial Offices | New Parliament & Ministerial Offices | New |  | Rarotonga |  | Cat.4 |  |  | X | X | X | 10000 | 10000 | [13 empty] | 1 | 4 | 5
Buildings | CIIC | CIIC | Rarotonga Government Buildings | Vaikapuangi Government Office Complex | All encompassing Gvt building proposal downtown | New |  | Rarotonga |  | Cat.5 |  |  | X | X | X | 56000 | 56300 |  |  | 2 | [6 empty] | 8.8 | 22 | 13 | 9.5 | 1 |  |  | Prelim design complete, will need to be staged.
Coastal | ICI | ICI | National Coastal Protection Program | Pa Enua Coastal Erosion Protection | Assessment and construction | Study |  | Cook Islands |  |  | X |  | X | X | X | 1200 | 1200 |  |  |  | 0.1 | 1 | 0.1 | [10 empty] | To be scoped and designed
Coastal | ICI | ICI | National Coastal Protection Program | Northern Coastal Erosion and Protection | Various island requirements | Upgrade |  | Northern |  |  | X |  |  | X | X | 2350 | 2400 | GCF |  |  |  | 0.8 | 0.8 | 0.8 | [9 empty] | To be scoped and designed
Coastal | ICI | ICI | National Coastal Protection Program | Pukapuka Causeway Protection | Upgrade of causeway road due to higher sea activity | Upgrade |  | Pukapuka | C1 |  | X |  |  | X | X | 1000 | 1000 |  |  |  |  | 1 | [11 empty] | Needs FS update
Coastal | ICI | ICI | National Coastal Protection Program | Pukapuka Cyclone Shelter Access Road | To provide a suitable vehicle access to shelter | Upgrade | CO | Pukapuka | C1 |  | X |  |  | X | X | 500 | 500 |  |  |  |  | 0.5 | [11 empty] | Should sit with above
Coastal | ICI | ICI | National Coastal Protection Program | Aroa Stream Embankment | Upgrade of stormwater system part of island wide Pro | Upgrade |  | Rarotonga |  |  | X |  |  |  | X | 500 | 500 | CIG |  | 0.5 | [13 empty] | To be scoped and designed
Coastal | ICI | ICI | National Coastal Protection Program | Avana Coastal Protection | Small CCAF project started - to be extended. | Upgrade |  | Rarotonga |  |  | X |  |  | X | X | 500 | 500 |  |  |  | 0.5 | [12 empty] | To be scoped and designed
Coastal | ICI | ICI | National Coastal Protection Program | Coastal Management and Mitigation | Critcal zones around island to be scoped and designed | Study |  | Rarotonga |  |  | X |  | X | X |  | 650 | 600 |  |  | 0.15 | 0.15 | 0.15 | 0.15 | [10 empty] | To be scoped and designed
Education | MFEM | MFEM | National Tertiary Campus Improvements | USP Campus Construction | Campus, dorm and faculty housing (Scoping study to confirm) | New |  | Cook Islands |  |  |  |  | X | X | X | 12500 | 12500 |  |  | 0.5 |  | 3 | 6 | 3 | [9 empty] | Will require detailed design, and construction
Education | MOE | MOE | National Tertiary Campus Improvements | Education Infrastructure Master Plan |  | Study |  | Cook Islands |  |  |  |  | X |  |  | 200 | 200 |  |  |  | 0.2
Education | CIIC | CIIC | Rarotonga Education Infrastructure Program | Tereora College Redevelopment Stages 2 and 3 | Stage 2 upgrade of the academic learning centres. Stage 3 Princess Anne Hall upgrades for the Facaulty of Arts | Upgrade |  | Rarotonga |  | Cat.4 |  |  |  | X | X | 24000 | 25000 | [6 empty] | 1 | 7 | 9 | 8 | [5 empty] | X
Education | CIIC | CIIC | Rarotonga Education Infrastructure Program | Tereora Pa Enua Hostel | Hostel for the Pa Enua students | New |  | Rarotonga | [5 empty] | X | X | 1000 | 7300 |  |  |  | 0.3 | 7
Energy | TMU | TMU | Aitutaki Renewable Energy Program | Aitutaki Solar Stage 2 | Scoping and Implementation | Upgrade |  | Aitutaki |  | Cat.4 | X |  |  | X | X | 7000 | 7000 |  |  |  |  | 3.5 | 3.5
Energy | TAU | TAU | Northern Renewable Energy Program | Northern Battery Replacement & Upgrades |  | Renew |  | Northern | C2 |  | X |  |  |  | X | 5000 | 5000 |  |  |  | 2.1 | 2.1 | 0.8
Energy | TAU | TAU | Rarotonga Energy Upgrades | 6MW PV Generation Contract |  | Upgrade |  | Rarotonga | C2 | Cat.4 |  |  |  | X | X |  | 0
Energy | TAU | TAU | Rarotonga Energy Upgrades | Private Sector Generation | Feasibility? Maybe scrapped | Study |  | Rarotonga |  | Cat.4 |  |  | X |  |  | 0 | 0 | [16 empty] | Private funded power scheme
Energy | TAU | TAU | Rarotonga Energy Upgrades | Energy Production/Distribution Upgrade |  | Upgrade |  | Rarotonga |  | Cat.4 |  |  |  | X | X | 0 | 0
Energy | TAU | TAU | Rarotonga Energy Upgrades | TAU Generation Projects |  | Upgrade |  | Rarotonga |  | Cat.4 |  |  |  | X | X | 21000 | 21000 |  | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1
Energy | TAU | TAU | Rarotonga Energy Upgrades | Network Stage 2 |  | Upgrade |  | Rarotonga |  | Cat.4 |  |  |  | X | X | 10000 | 10000 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Energy | TAU | TAU | Rarotonga Energy Upgrades | Upgrade Existing Grid and Equipment |  | Upgrade |  | Rarotonga |  | Cat.4 |  |  |  | X | X | 5067 | 5100 |  | 0.51 | 0.51 | 0.51 | 0.51 | 0.51 | 0.51 | 0.51 | 0.51 | 0.51 | 0.51
Energy | TAU | TAU | Rarotonga Renewable Energy Program | Renewable Energy Project Management |  | New |  | Rarotonga |  | Cat.4 | X |  |  | X | X | 0 | 0
Health | MOH | CIIC | National Health Infrastructure Program | Mental Health Facility |  | New |  | Cook Islands | C1 |  |  |  | X | X | X | 900 | 900 | CIG |  | 0.9
Health | INTAFF | INTAFF | National Health Infrastructure Program | Aged Care Facility |  | New |  | Cook Islands |  |  |  |  | X | X | X | 4250 | 4250 | ADB |  | 0.25 | 0.5 | 3 | 0.5
Health | MOH | MOH | National Health Infrastructure Program | TMO - Primary Care Centre of Excellence | Construction of a Primary Care and Pandemic Centre at Tupapa to replace the sub standard health facillity and infrastructure. | Upgrade |  | Rarotonga |  |  |  |  | X | X | X | 11000 | 11000 | [5 empty] | 5 | 6
Health | MOH | MOH | National Health Infrastructure Program | New Rarotonga Hospital |  | New |  | Rarotonga |  | Cat.5 |  |  | X | X | X | 60000 | 60000 |  |  |  | 5 | 10 | 10 | 10 | 10 | 10 | 5
ICT | OPM | OPM | National ICT Enhancements | ICT Server Room, Network Upgrade |  | New |  | Cook Islands | C2 |  |  |  |  | X | X | 1700 | 1700 | CIG |  | 1.7
ICT | ACL | ACL | National ICT Enhancements | Southern Submarine Fibre Optic Cable | Submarine fibre-optic cable connecting of the Sth Cooks | New |  | Southern |  |  |  |  | X | X | X | 10000 | 500 | [13 empty] | 0.5 |  | x
Marine | MFEM | MFEM | (unassigned) | The National Boat | Development of a purpose built boat to service the Cook Islands | New |  | Cook Islands |  |  |  |  | X | X | X | 10000 | 10500 | [5 empty] | 2 | 8 | [6 empty] | 0.5
Marine | CIPA | CIPA | Aitutaki Harbour and Marina Improvements | Aitutaki Harbour Passage Dredging |  | Renew |  | Aitutaki | C2 | [5 empty] | X | 1800 | 1800 | CIG | 1.8 | [14 empty] | New Dredge about to be received.
Marine | CIPA | CIPA | Aitutaki Harbour and Marina Improvements | Aitutaki (Orongo) Marina Improvements | Marina upgrade, passage dredging and town centre dev | Upgrade |  | Aitutaki |  | Cat.4 |  |  |  | X | X | 13000 | 0
Marine | ICI | ICI | Northern Harbour Improvements | Manihiki Jetty Construction |  | New |  | Manihiki | [5 empty] | X | X | 360 | 400 |  |  |  |  | 0.4
Marine | ICI | ICI | Northern Harbour Improvements | Nassau Harbour Improvements | Design and construction | Upgrade |  | Nassau | C2 |  |  |  |  | X | X | 4650 | 4600 |  |  |  | 4.6 | [12 empty] | Scping and survey recenty carried out
Marine | ICI | ICI | Northern Harbour Improvements | Penrhyn Harbour Assessment | Feasibility study for main island facility and potential for export fish offloading | Study |  | Penrhyn | C2 |  |  |  | X |  |  | 250 | 250 |  |  | 0.25 | [13 empty] | Awaiting feasibility study for costs
Marine | ICI | ICI | Northern Harbour Improvements | Penrhyn (TeTautua & Omoka) Port Facilities | Jetty construction for separate villages | Upgrade |  | Penrhyn | [5 empty] | X | X | 1000 | 1000 | CIG |  |  | 1
Marine | ICI | ICI | Northern Harbour Improvements | Penrhyn Harbour Upgrade | Upgraded harbour and protection works for relocated fuel depot | Upgrade |  | Penrhyn | [5 empty] | X | X | 20000 | 20000 | [5 empty] | 10 | 10
Marine | ICI | ICI | Northern Harbour Improvements | Rakahanga Harbour Improvement |  | Study |  | Rakahanga | C2 |  |  |  | X |  |  | 120 | 120 |  |  | 0.12
Marine | ICI | ICI | Pukapuka Harbour Improvements | Pukapuka Jetty Development |  | Upgrade |  | Pukapuka | [5 empty] | X | X | 360 | 400 |  |  |  |  | 0.4
Marine | ICI | ICI | Pukapuka Harbour Improvements | Pukapuka Harbour Upgrade |  | Upgrade |  | Pukapuka | [5 empty] | X | X | 4000 | 4000 |  |  |  |  | 4
Marine | ICI | ICI | Rarotonga Harbour Improvements | National Harbours Road Map |  | Study |  | Cook Islands | C2 |  |  |  | X |  |  | 300 | 300 |  |  | 0.3
Marine | CIPA | CIPA | Rarotonga Harbour Improvements | Avatiu Western Marina Extension | Including cyclone protection works | Upgrade |  | Rarotonga |  |  | X |  |  | X | X | 4000 | 4000 | [7 empty] | 2 | 2
Marine | CIPA | CIPA | Rarotonga Harbour Improvements | Avatiu Harbour Entrance Widening |  | Upgrade |  | Rarotonga | [5 empty] | X | X | 1000 | 1000 | [7 empty] | 1
Marine | CIPA | CIPA | Rarotonga Harbour Improvements | Avatiu Eastern Breakwater |  | Renew |  | Rarotonga | [5 empty] | X | X | 1000 | 1000 | [8 empty] | 1
Marine | ICI | ICI | Southern Harbour Improvements | Atiu Wharf Upgrade |  | Upgrade |  | Atiu | [5 empty] | X | X | 1500 | 1500 |  |  |  |  | 1.5
Marine | ICI | ICI | Southern Harbour Improvements | Mangaia Harbour Climate Resilience |  | Upgrade | ON | Mangaia | C2 |  |  |  |  | X | X | 985 | 0 | CIG
Marine | ICI | ICI | Southern Harbour Improvements | Mauke Harbour Upgrade |  | Upgrade |  | Mauke | [5 empty] | X | X | 360 | 400 |  |  | 0.4
Marine | ICI | ICI | Southern Harbour Improvements | Mitiaro Wharf Upgrade |  | Upgrade |  | Mitiaro | [5 empty] | X | X | 500 | 500 |  |  | 0.5
Municipal | CIIC | CIIC | Rarotonga Township Enhancements | Avatiu Port Walkway and Marina |  | New |  | Rarotonga | [5 empty] | X | X | 1000 | 1000 | [5 empty] | 0.1 | 0.9
Municipal | CIIC | CIIC | Rarotonga Township Enhancements | Markets and Constitution Park Reorganisation |  | New |  | Rarotonga | [5 empty] | X | X | 2250 | 2200 |  |  | 0.3 | 0.3 | 0.5 | 1.1
Municipal | ICI | ICI | Rarotonga Township Enhancements | Two Roads Parking, Lighting and Footpaths |  | New |  | Rarotonga | [5 empty] | X | X | 2000 | 2000 | [6 empty] | 1 | 1
Municipal | CIIC | CIIC | Rarotonga Township Enhancements | Coastal Prominade and Town Centre Enhancements |  | New |  | Rarotonga | [5 empty] | X | X | 2000 | 2000 | [5 empty] | 0.5 | 1.5
Municipal | ICI | ICI | Rarotonga Township Enhancements | Panama Walk and Cycleway |  | New |  | Rarotonga | [5 empty] | X | X | 2000 | 2000 | [7 empty] | 1 | 1
Municipal | CIIC | CIIC | Rarotonga Township Enhancements | Nikao Social Centre |  | New |  | Rarotonga | [5 empty] | X | X | 7000 | 7125 | [6 empty] | 0.175 | 1.95 | 4.6 | 0.4
Road | ICI | ICI | Rarotonga Bridge Renewals | Empire Bridge Replacement | Required due to safety issues | Renew | CO | Rarotonga | C1 |  | X |  |  | X | X | 3600 | 3800 |  |  | 1.9 | 1.9 | [12 empty] | Advertised for tenders Feb 2021
Road | ICI | ICI | Rarotonga Bridge Renewals | Taipara Bridge Replacement |  | Renew |  | Rarotonga | C1 |  | X |  |  | X | X | 3300 | 3300 |  |  |  |  | 1.7 | 1.6
Road | ICI | ICI | Rarotonga Bridge Renewals | Sheraton Bridge Replacement | Design and construction | Renew | CO | Rarotonga | C1 |  | X |  |  | X | X | 3300 | 3300 |  |  |  | 1.7 | 1.6 | [11 empty] | Decision around location to be resolved.
Road | ICI | ICI | Rarotonga Bridge Renewals | Miscellaneous Bridge Upgrades |  | Renew |  | Rarotonga | C2 |  | X |  |  | X | X | 8300 | 8300 | [6 empty] | 1.7 | 1.6 | 1.7 | 1.6 | 1.7
Road | ICI | ICI | Rarotonga Road Improvements | Arorangi Drainage Improvements | Drain/Culvert upgrades to cater for more intense rain. | Study | PI | Rarotonga | C2 |  |  |  | X |  |  | 1060 | 1100 |  |  | 1.1 | [13 empty] | Should follow Muri drainage improvements
Road | ICI | ICI | Rarotonga Road Improvements | Culvert Replacement & Improvement | Rarotonga wide renewal of culverts | Upgrade | PI | Rarotonga | [5 empty] | X | X | 1000 | 1000 |  |  |  |  | 0.5 | 0.5 | [10 empty] | Ditto
Road | ICI | ICI | Rarotonga Road Improvements | Aroko Road Widening Project | Increase road width for safety | Upgrade | CO | Rarotonga | [5 empty] | X | X | 750 | 750 |  |  | 0.75 | [13 empty] | Awaiting completion of Drainage Works
Road | ICI | ICI | Rarotonga Road Improvements | Muri Area Upgrade with Footpaths | Kerb & Channel & Footpaths proposed on sea side | Upgrade | PI | Rarotonga | [5 empty] | X | X | 1500 | 1500 |  |  |  |  | 1.5 | [11 empty] | New project in high tourist area
Road | ICI | ICI | Rarotonga Road Improvements | Road Safety Improvements | Signage, guard railing etc | Upgrade | PI | Rarotonga | [5 empty] | X | X | 1102 | 1100 |  |  | 0.2 | 0.3 | 0.3 | 0.3 | [10 empty] | Ongoing
Road | ICI | ICI | Rarotonga Road Maintenance Program | Roads Planned Periodic Maintenance | Resurfacing and rehabilitation | Renew | PI | Rarotonga | [5 empty] | X | X | 18800 | 18000 |  |  | 4.5 | 4.5 | 4.5 | 4.5 | [10 empty] | Ongoing
Road | ICI | ICI | Southern Road Improvement Program | Mangaia Road Upgrades | Fixing the main artery through Mangaia | Upgrade |  | Mangaia | C1 |  |  |  |  | X | X | 3000 | 3000 |  |  |  | 3
Road | ICI | ICI | Southern Road Improvement Program | Mauke Road Resurfacing and Rehabilitation | Resurfacing and rehabilitation | Renew |  | Mauke | [5 empty] | X | X | 1200 | 1200 |  |  | 1.2
Road | ICI | ICI | Southern Road Improvement Program | Mitiaro Road Resurfacing and Rehabilitation | Resurfacing and rehabilitation | Renew |  | Mitiaro | [5 empty] | X | X | 800 | 800 |  |  | 0.4 | 0.4
Sanitation | ICI | ICI | Northern Sanitation Improvements | Northern Sanitation Upgrades |  | Renew |  | Northern |  |  |  |  | X | X | X | 2200 | 2200 |  |  |  | 0.2 |  |  |  | 1 | 1 | [7 empty] | Combine with Sth Group
Sanitation | MOH | MOH | Northern Sanitation Improvements | Pukapuka Household Sanitation Facilities |  | New |  | Pukapuka | C1 | [5 empty] | X | 970 | 970 | CIG |  | 0.97
Sanitation | MFEM | MFEM | Rarotonga Sanitation Improvements | MTVKTV Long-term Sanitation Upgrades | Reticulated system for Rarotonga wih start in Muri area. | Upgrade |  | Rarotonga | C2 | Cat.5 |  |  |  | X | X | 50000 | 50000 | NZAID | [5 empty] | 1 | 5 | 10 | 15 | 15 | 4 |  |  |  |  | GHD consultants have ben scoping possibilities
Sanitation | ICI | ICI | Rarotonga Sanitation Improvements | Tepuka Sanitation Improvement | Upgrade of current treatment and discharge system. | Upgrade |  | Rarotonga | C2 | Cat.4 |  |  |  | X | X | 5000 | 5000 | CIG |  | 1 | 2 | 2 | [11 empty] | Heavy populated area close by schools.
Sanitation | ICI | ICI | Southern Sanitation Improvements | Aitutaki Sanitation Upgrades | TBD - Must look at options for desludging septic | Upgrade |  | Aitutaki | C2 |  |  |  |  | X | X | 3000 | 3000 | CIG |  |  |  | 0.5 | 2.5
Sanitation | ICI | ICI | Southern Sanitation Improvements | Sanitation Management Study | Feasibility study (Pa Enua and Rarotonga) | Study |  | Cook Islands |  |  |  |  | X |  |  | 160 | 200 | CIG |  | 0.2
Sanitation | ICI | ICI | Southern Sanitation Improvements | Southern Sanitation Upgrades | Subject to the Scoping Study | Renew |  | Southern |  |  |  |  | X | X | X | 2150 | 2200 |  |  |  | 0.2 |  |  |  | 1 | 1
Waste | ICI | ICI | Northern Solid Waste Program | Northern Waste Centres Upgrade |  | Upgrade |  | Northern | [6 empty] | X | 100 | 0
Waste | ICI | ICI | Rarotonga Solid Waste Management Program | Nation Waste Management Strategy | Scoping Options and feasibility | Study |  | Rarotonga | C1 |  |  |  | X |  |  | 500 | 500 |  |  | 0.5
Waste | ICI | ICI | Rarotonga Solid Waste Management Program | Hazardous Waste Handling Facilities | Feasibility / design study required | Study |  | Rarotonga | C1 |  |  |  | X |  |  | 100 | 100 |  |  | 0.1 | [13 empty] | Part of overall waste management strategy
Waste | ICI | ICI | Rarotonga Solid Waste Management Program | Solid Waste Incinerator | Feasibility and construction | New |  | Rarotonga | C2 |  | X |  | X | X | X | 5060 | 5000 |  |  |  |  | 5 | [11 empty] | Needs to be fully scoped and planned.
Waste | ICI | ICI | Rarotonga Solid Waste Management Program | Recycling Transfer Facility | Feasibility / design study required | Study |  | Rarotonga | C2 |  | X |  | X |  |  | 200 | 200 |  |  | 0.2 | [13 empty] | Upgrade and extension
Waste | ICI | ICI | Rarotonga Solid Waste Management Program | TGA Rarotonga Compost Facilities | Feasibility / design study required | New |  | Rarotonga |  |  | X |  |  | X | X | 500 | 0 | [16 empty] | Part of overall waste management strategy
Waste | ICI | ICI | Southern Solid Waste Management Program | Southern Waste Centres Upgrade |  | Upgrade |  | Southern | [6 empty] | X | 200 | 0
Water | ICI | ICI | Aitutaki Water Security Program | Aitutaki Domestic Water Tanks | Water tanks to private homes | New | CO | Aitutaki | C2 |  | X |  |  |  | X | 500 | 500 |  | 0.5 | [14 empty] | 290 homes left to complete
Water | ICI | ICI | Aitutaki Water Security Program | Aitutaki Upgrade Reticulation System |  | Upgrade |  | Aitutaki |  | Cat.4 | X |  |  | X | X | 5000 | 5000 |  |  |  |  | 2.5 | 2.5
Water | ICI | ICI | Aitutaki Water Security Program | Aitutaki Upgrade of Galleries and Reticulation |  | Upgrade |  | Aitutaki |  |  | X |  | X | X | X | 5200 | 5200 | CIG |  |  | 0.2 | 2.5 | 2.5
Water | ICI | ICI | Northern Water Security Program | Northern Community Water Tanks Rehabilitation | Nth Group tank upgrades need to continue | Renew |  | Northern | C2 |  | X |  |  |  | X | 1200 | 1200 | UNDP/NZ | 0.4 | 0.4 | 0.4 | [12 empty] | Many completed still others need repairs.
Water | ICI | ICI | Northern Water Security Program | Pukapuka Water Gallery Improvement | Gallery Upgrade required | Upgrade |  | Pukapuka | C2 |  | X |  |  |  | X | 120 | 100 | CIG |  |  |  | 0.1 | [11 empty] | I Council do not want underground water taped.
Water | TTV | TTV | Rarotonga Water Security Program | Sub Main Replacement Sector 5 - Titikaveka | Replacement AC sub mains back road Titikaveka | New |  | Rarotonga | C2 | Cat.5 |  |  |  | X | X | 3366 | 4200 | CIG | 0.6 | 1 | 1.6 | 1 | x | [10 empty] | High priority to reduce pipe losses.
Water | TTV | TTV | Rarotonga Water Security Program | SCADA Installation | Supervisory Control and Data Acquisition | New |  | Rarotonga | C2 | Cat.5 |  |  |  | X | X | 1850 | 1900 | CIG | 0.1 | 0.9 | 0.9 |  | x | [10 empty] | Using IT monitoring and control of site systems.
Water | TTV | TTV | Rarotonga Water Security Program | Reservoir & Tank Meters for Turbidity | Meters at intake sites that were missing from TMV. | New |  | Rarotonga | C2 | Cat.5 |  |  |  |  | X | 200 | 200 | CIG | x | 0.2 | x | [12 empty] | Part of getting TTV into full quality mode
Water | TTV | TTV | Rarotonga Water Security Program | Sludge Disposal | Land and facilities required for sludge disposal | New |  | Rarotonga | C2 | Cat.5 |  |  | X | X | X | 200 | 200 | CIG | x | 0.2 | [13 empty] | Suitable land identified. Requires EIA
Water | TTV | TTV | Rarotonga Water Security Program | Water Network Infrastructure/Laboratory Assets | Facilities req to check filter & water Quality | New |  | Rarotonga | C2 | Cat.5 |  |  |  | X | X | 100 | 200 | CIG | x | 0.2 | [13 empty] | Part of getting TTV into full quality mode
Water | TTV | TTV | Rarotonga Water Security Program | CCTV Mapping of Network & Pipe Cleaning | Confirm network and cleaning procedure | New |  | Rarotonga | C2 | Cat.5 |  |  |  | X | X | 581 | 581 | CIG | x | 0.581 | [13 empty] | Required to ensure potable water to customers
Water | TTV | TTV | Rarotonga Water Security Program | Piping To Fix Deadlegs | Many deadlegs need to be eliminated or renewed | New |  | Rarotonga | C2 | Cat.5 |  |  |  |  | X | 1500 | 1500 | CIG |  | 1.5 | [13 empty] | A must as part of process towards potable water
Water | TTV | TTV | Rarotonga Water Security Program | Repairs to Mains | Continual replacement of stage 1 faulty system | New |  | Rarotonga | C2 | Cat.5 |  |  |  |  | X | 30000 | 30000 | CIG |  | 3 | 3 | 3 | 5 | 5 | 5 | 3 | 3
Water | TTV | TTV | Rarotonga Water Security Program | Water Meters - Purchase and Install | Installation of water meters to all connections | New |  | Rarotonga |  | Cat.5 | X |  |  | X | X | 8000 | 8000 | CIG | 1 | 2 | 2 | 2 | 1 | [10 empty] | Needs to be in place before any charging !!!
Water | TTV | TTV | Rarotonga Water Security Program | UV Station Maintenance Testing & New School UV's | Continual UV maintenance and new school unit instal | New |  | Rarotonga |  | Cat.5 |  |  |  | X | X | 373.6 | 400 | CIG | 0.4 | [14 empty] | Provides potable water to general public
Water | ICI | ICI | Southern Water Security Program | Aitutaki Water Ground Water Study | Following SPC scoping mission in 2020 | Study |  | Aitutaki | C2 |  | X |  | X |  |  | 500 | 500 |  |  |  | 0.5
Water | ICI | ICI | Southern Water Security Program | Atiu Water Reticulation System | Reticulaton system for Villages (water sourcing required) | New |  | Atiu | C2 |  |  |  |  | X | X | 3000 | 3000 |  |  |  | 1.5 | 1.5 | [11 empty] | To be fuly scoped for gound water source
Water | ICI | ICI | Southern Water Security Program | Atiu Community Water Storage | Repair of a number of 45,000 lt tanks | New |  | Atiu | C2 |  | X |  |  |  | X | 200 | 200 |  |  |  | 0.2 | [12 empty] | Funding to be determined
Water | ICI | ICI | Southern Water Security Program | Mangaia Water Distribution Upgrade | Oneroa Village supply upgrade | Upgrade |  | Mangaia | C2 | [5 empty] | X | 1500 | 1900 | CIG | 0.4 | 0.8 | 0.7 | [12 empty] | Scoping and Design underway.
Water | ICI | ICI | Southern Water Security Program | Mitiaro Water Tanks | Continuation of upgrade to community water system. | New |  | Mitiaro | C2 |  | X |  |  |  | X | 265 | 300 |  |  |  |  | 0.3 | [11 empty] | Scoping and Design underway.
Water | ICI | ICI | Southern Water Security Program | Mitiaro Water Source and Distribution Improvement | 2km pipeline construction | New |  | Mitiaro | C2 |  | X |  |  | X | X | 800 | 0
Water | ICI | ICI | Southern Water Security Program | Southern Water Ground Water | Developing Reticulated systems in Mitiaro & Mangaia | New |  | Southern | C2 |  | X |  | X | X | X | 1600 | 1600 |  |  |  | 0.4 | 0.4 | 0.4 | 0.4
[16 empty] | 662569.6 |  |  | 12.67 | 46.951 | 66.86 | 95.02 | 82.16 | 64.685 | 47.16 | 53.91 | 50.41 | 53.31 | 23 | 18 | 4.5 | 16 | 5
[20 empty] | 23.1 | 19 | 42
662569.6