## Project List
Appendix F: Project Long and Short List
| 1 | 2 |  | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | Likely Funding Source(s) |  |  |  | 16 | 17 | 18 | 18b | 19 | 20 | 21
# | Proj. Ref. | Early Screening MCA Req'd (ext fund) | 2024/25 NPP submitted? | Sector Code | Project Type | Major Asset Class | Lead Unit | Others | Key Driver | Program Level Budget Entry? | Program Name (leave blank if project is not part of a wider program) | Project Name (leave blank if entry is a program level budget) | Brief Description | Status | Latest Estimate ($) | Curr. | Agency | Gov.Grant | Dev. Partner | Private | Funding provided by (or in discussion with) | Cost Estimate (AU$,000) | Actual / Estimated Start (Fin.Year) | % Complete | Notes | Added by | Identified In (sourced from)…
1 | AIR-11 | Yes | Yes | Aviation | New | Buildings | DOT |  | Ministry | Yes | Nauru Airport Terminal Redevelopment Program | - | To upgrade the existing terminal with increase in floor space of arrival, departure lounge. Adding new duty free premises, introducing elevated parking lot, introduction of centralised air conditioner. Increasing the solar roofing within the airport premises. A mini sewage treatment plant. | Planned | 20000000 | AUD |  |  | X |  |  | 20000
2 | AIR-12 | No |  | Aviation | Upgrade | Runway Pavements | DOT |  | Ministry | No |  | Runway Resurfacing | Resurface the airstrip at Nauru airport | Ongoing | 40000000 | AUD |  |  | X |  | AIFFP | 40000 | 2022-2024 |  | $3 million will be provided in financial year 2022-23. | GF | Dev. Fund Projection 22-23
3 | AIR-13 | Yes | Yes | Aviation | Purchase | Specialty Equipment | DOT |  | Ministry | No |  | Backup Generator for the International Airport | Need to replace the existing backup generator which is currently down | Planned | 120000 | AUD | X | X |  |  |  | 120
4 | COM-11 | No |  | Cultural | Upgrade | Buildings | DCA |  | Ministry | No | Museum Improvements | Rebuilding Museum Building | Expand museum building to provide more space, new display cabinets, climate control | Planned |  | AUD |  |  | X |  |  | 0 | 2026
5 | COM-12 | No |  | Cultural | Upgrade | Buildings | DCA |  | Ministry | No | Museum Improvements | Equipment Room | Provide office for digitisation equipment | Planned |  | AUD |  |  | X |  |  | 0 | 2024
6 | EDU-11 | No |  | Education | Upgrade | Building | DOET |  | Ministry | Yes | Canteens in Schools | - | Construct new canteens for Yaren Primary, Nauru Primary and Nauru College | Planned | 200000 | AUD |  | X |  |  | GON | 200 | 2023-2024
7 | EDU-12 | No |  | Education | Renewal | Buildings | DOET |  | Ministry | Yes | Capital Maintenance for Nauru Secondary Schools | - | Require full maintenance for Nauru Secondary School (all classrooms) | Planned |  | AUD |  | X | X |  |  | 0
8 | EDU-13 | No |  | Education | Renewal | Buildings | DOET |  | Ministry | Yes | Roof Repairs to Infant Schools | - | Replace alll Roofings, gutters, ceilings for all Nauru Infant Schools | Planned |  | AUD |  | X | X |  |  | 0
9 | EDU-14 | No |  | Education | Renewal | Building | DOET |  | Ministry | Yes | School Building Renovations (2022-23) | - | Nauru Seconary School Classrooms, Nauru Primary School Classrooms, Cafeteria, Recreational Hall, Dining Hall, Recreational Hall, NSS School Fence | Ongoing | 557000 | AUD |  | X |  |  | GON | 557 | 2022-2023 |  | Funded through GON |  | Education project list
10 | EDU-15 | No |  | Education | Renewal | Building | DOET |  | Ministry | Yes | School Building Renovations (2023-24) | - | MIS School Fence, MIS Tuck-shop, MIS School Hall, MIS School Roofing, NPS Verandah, AIS Roofing, NIS Roofing, AIS Flooring and Wall replacement | Budgeted | 240000 | AUD |  | X |  |  | GON | 240 | 2023-2024 |  | Funded through GON
11 | EDU-16 | No |  | Education | Renewal | Building | DOET |  | Ministry | Yes | School Building Renovations (2024+) | - | Renovation for Nauru Primary Schools, Renovation for Nauru College, Renovation for Yaren Primary School, Remodel Nauru Secondary School Gym, Remodel Nauru College Extra-Curricular Classes | Planned | 500000 | AUD |  | X |  |  | GON | 500 | 2023-2024 |  | Funded through GON
12 | EDU-17 | No |  | Education | New | Building | DOET |  | Ministry | No |  | Nauru College Shade sail | To construct a shade or sail at Nauru College | Appraising |  | AUD |  |  | X |  | AusAID | 0 | 2023-2024 |  | Funding is from Aid |  | AUSAID Project
13 | EDU-18 | No |  | Education | Renewal | Building | DOET |  | Ministry | No |  | Sacred Heart Infant Classroom tiling | To renew all the tilings for the 5 classes. | Appraising | 22000 | AUD |  |  | X |  | AusAID | 22 | 2023-2024 |  | Funding is from Aid |  | AUSAID Project
14 | EDU-27 | No |  | Education | New | Buildings | DOET |  | Ministry | No |  | New Students Toilet for Nauru Primary School | Construct new students toilet for Nauru Primary School | Planned |  | AUD |  | X | X |  |  | 0
15 | EDU-19 | No |  | Education | New | Buildings | TVET |  | Ministry | No | Greening TVET System | Solar Panels | Installation of solar panel system | Appraising |  | AUD |  | X | X |  | NZMFAT | 0
48 | EDU-20 | No |  | Education | New | Buildings | TVET |  | Ministry | No | Quality Access to Education and Training | Warehouse Structure | For outdoor practical training. | Planned |  | AUD |  | X | X |  |  | 0
17 | EDU-21 | Yes | No | Education | Upgrade | Buildings | TVET |  | Ministry | No | Quality Access to Education and Training | Hospitality Kitchen Improvements | To Commercial kitchen Australian standard. | Planned | 3000000 | AUD |  | X | X |  |  | 3000
18 | EDU-22 | No |  | Education | Upgrade | Buildings | TVET |  | Ministry | No | Quality Access to Education and Training | Fashion and Design Building Improvement | Fashion & Design workshop. | Planned |  | AUD |  | X | X |  |  | 0
19 | EDU-23 | No |  | Education | Upgrade | Buildings | TVET |  | Ministry | No | Quality Access to Education and Training | ICT Training Room | Converting storage space to an ICT training room. | Planned |  | AUD |  | X | X |  |  | 0
20 | EDU-24 | Yes | No | Education | Upgrade | Buildings | TVET |  | Ministry | No | Quality Access to Education and Training | Engineering Industrial Workshop Improvements | Improvement to Engineering workshop | Planned | 3000000 | AUD |  | X | X |  |  | 3000
21 | EDU-25 | Yes | No | Education | New | Buildings | TVET |  | Ministry | No |  | New Multipurpose Building for Life Skills | Multi purpose workshop for life skills program training. | Planned | 5000000 | AUD |  | X | X |  |  | 5000 | 2024
22 | EDU-26 | No |  | Education | Upgrade | Buildings | TVET |  | Ministry | No |  | Campus Improvement | Campus Improvement for inclusivity - Friendly to disability. | Planned |  | AUD |  | X | X |  |  | 0
23 | EMG-11 | Yes | Yes | Emergency | Purchase | Specialty Vehicles | NES |  | Ministry | No |  | Replacement of Fire Trucks | Airport categorisation is about to change with the purchase of the new 737-800 cargo plane. Fire service cannot currently meet the requirements of this categorisation. Existing fire trucks are old and access to parts is becoming a major issue | Planned | 2000000 | AUD |  |  | X |  |  | 2000 | 2024
24 | EMG-12 | No |  | Emergency | Upgrade | Buildings | NES |  | Ministry | No |  | Rehabilitation of Fire Station | Replace roof and strengthen building structure | Planned | 100000 | AUD |  | X |  |  |  | 100 | 2026
25 | EMG-13 | No |  | Emergency | New | Buildings | NES |  | Ministry | No |  | New Department of Emergency Services Building | New building to house all functions of the NES, including meteorology, DRM, fire and ambulance. | Planned | 4100000 | AUD |  |  | X |  |  | 4100 | 2025
26 | EMG-14 | No |  | Emergency | New | Specialty Equipment | NES |  | Ministry | No |  | Automatic Weather Station | To replace the existing manual system. Will provide real time weather updates, as well as improved monitoring data | Planned | 30000 | AUD |  |  | X |  |  | 30 | 2025
27 | EMG-15 | No |  | Emergency | New | Specialty Equipment | NES |  | Ministry | No |  | Disaster Early Warning System | Nauru currently has no system for warning residents of impending disasters. Tsunami in particular are known to be a hazard. Nauru needs a network of sirens to inform residents to move to higher ground. This needs to be accompanied by a network of evacuation routes, muster points and a disaster response plan | Planned | 5000000 | AUD |  |  | X |  |  | 5000 | 2026
28 | EMG-16 | No |  | Emergency | Renewal | Specialty Vehicles | NES |  | Ministry | No |  | Replacement Ambulance | The existing ambulances in Nauru are coming to the end of their life and will need replacing | Planned | 125000 | AUD |  |  | X |  |  | 125 | 2026
29 | ENE-21 | No |  | Energy | Tech. Assist. | Other Assets | DCCNR | GCF | Ministry | No |  | OTEC | Ocean Thermal Energy - feasibility study and EIA scoping done. Renewable energy scheme to create electricity from seawater. By product is fresh water - enough for the whole island. 1-2 Megawatt. | Planned | 70000000 | USD | [5 empty] | 109375
30 | ENE-11 | No |  | Energy | New | NUC-E | NUC-E | NUC | Ministry | No | 6MW ADB Solar Plant | High Speed Relocation | Revisiting 2019 project that was discarded by previous admin. Relocate 6x1MW high speed Gen Sets to Solar Farm site | Appraising | 1600000 | AUD |  | X |  |  | NUC/Donor | 1600 | 2027 |  | Relocation of high speed genset to higher ground to support Nauru Emergency Services | Mark Hiram
31 | ENE-12 | No |  | Energy | New | Solar Power | NUC-E |  | Ministry | No | 6MW ADB Solar Plant | Extended Battery Storage | Extended battery storage system for the 6MW solar energy farm | Planned | 550000 | AUD |  |  | X |  | ROC (Taiwan) | 550 | 2022- |  | Taiwan supports Nauru’s efforts to reduce reliance on fossil fuels through a solar panels project valued at AUD $552,105 | GF | Dev. Fund Projection 22-23
32 | ENE-13 | Yes | No | Energy | New | Transmission lines | NUC-E | NUC | Ministry | No | High Voltage 11KV Grid Extention | RPC 2 Grid Extension | Source funding to connect HV Grid Extension on Government infrastructure at topside that are currently energised by stand alone gensets | Planned | 900000 | AUD |  |  | X |  | EU/ADB | 900 | 2023-2025 |  | Feasibility study and technical assistance is required during implementation to address capacity building | Jonpeal | Newly proposed projectx. Current NIISP
33 | ENE-14 | Yes | No | Energy | Upgrade | Transmission lines | NUC-E | NUC | Ministry | No | Low Voltage Distribution Line Upgrade | Buada Low Voltage Underground Cable Upgrade | To replace existing undergound cables the whole of Buada District in which have deteriorated and is causing power flunctuations | Planned | 1200000 | AUD |  |  | X |  | EU/ADB | 1200 | 2023-2025 |  | Feasibility study and technical assistance is required during implementation to address capacity building | Jonpeal | Newly proposed projectx. Current NIISP
34 | ENE-15 | No |  | Energy | New | Solar Power | NUC-E | DCCNR | Ministry | Yes | Nauru Energy Efficiency on the Demand Side (NEEDS) | - | Support the achievement of the 30% energy efficiency target set in the Nauru Energy Road Map (NERM) | Ongoing | 1700000 | AUD |  |  | X |  | NZMFAT | 1700 | 2023 |  | AUD $1.7 million (NZD $1.8 million) will be provided in financial year 2022-23. | GF | Dev. Fund Projection 22-23
35 | ENE-16 | No |  | Energy | Tech. Assist. | NUC-E | NUC-E | NUC | Ministry | No |  | Hydro pump energy storage | Feasibility Study. Introduction of hydro pump system. GHD pre-feasibility study done. Looking for funding for feasibility study and implementation | Appraising | 300000 | AUD |  | X |  |  | NUC/Donor | 300 | 2030 |  | Long term renewable energy supply | Mark Hiram
36 | ENE-17 | No |  | Energy | New | Solar Power | NUC-E |  | Ministry | No | 6MW ADB Solar Plant | Solar Power Development Project | Involves the instalment of a 6MW solar energy farm with battery energy storage system ( for 30 mins) including institutional capacity development. | Ongoing | 22000000 | AUD |  |  | X |  | ADB | 22000 | 2018-2024 |  | Total budget of AUD $32.3 million (USD $22 million). 11.5m 2022/23 amd 5m 21/22 | GF | Dev. Fund Projection 22-23
37 | ENE-18 | Yes | No | Energy | Upgrade | Transmission lines | NUC-E | 28 | Ministry | No |  | Upgrade Substation at Location Area | Switch exisiting Air Break Switch (ABS) with Ring Main Unit (RMU). Current ABS are deteriorting and in dire need to replace | Planned | 1500000 | AUD |  |  | X |  | EU/ADB | 1500 | 2023-2026 |  | Purchase and deliver units for replacement | Jonpeal | Newly proposed projectx. Current NIISP
38 | ENE-19 | Yes | Yes | Energy | Upgrade | Other Assets | NUC-E | NUC | Importance | No |  | Upgrade 3.3kva Switch Gear at Power Station | Existing switch gear outdated >20years, spares are not available globally | Planned | 1102000 | AUD |  |  | X |  | EU/ADB | 1102 | 2023-2027 |  | Purchase and deliver units for replacement | Ken Blake | Newly proposed projectx. Current NIISP
39 | ENE-20 | Yes | Yes | Energy | Upgrade | Other Assets | NUC-E | NUC | Importance | No |  | Upgrade RMN, RME, and RMS Power Transformers | Existing 2.5MVA TRX are have become insufficent due to forever increasing demand, want to replace with 4.5MVA - urgent project as 1 already down, losing another would lead to load shedding - future proofing | Appraising | 1396000 | AUD |  |  | X |  | EU/ADB | 1396 | 2023-2028 |  | Purchase and deliver units for replacement | Ken Blake | Newly proposed projectx. Current NIISP
40 | ENE-23 | Yes | No | Energy | New | Specialty Vehicles | NUC-E | NUC | Ministry | No |  | 16 metre Cherry Picker | Acquisition of specialist vehicle to enable safe working around distribution pylons | Planned | 250000 | AUD | [5 empty] | 250
41 | ENE-22 | Yes | No | Energy | Renewal | Storage Tanks | VEI |  | Ministry | No |  | Fuel Tank Farm Repairs | Continuation of repairs and maintenance of the Tank Farm infrastructure to ensure safety and security of fuel supply on island | Ongoing | 1500000 | AUD |  | X |  |  |  | 1500 | 2023 |  |  | GF | 2022-23 Budget
42 | ENV-11 | No |  | Environment | Tech. Assist. | Multi-Asset | DCCNR |  | Ministry | No |  | Climate Change Risk Assessment | Risk assessment to understanding the scale, timing and cost of CC impacts on important national assests | Planned |  | AUD | [5 empty] | 0
43 | ENV-12 | No |  | Environment | Tech. Assist. | Other Assets | DCCNR | GCF | Ministry | No |  | Modelling Impact of Saltwater Intrusion | Modelling of impacts of salt intrusion into ground water | Planned |  | AUD | [5 empty] | 0
44 | ENV-26 | No |  | Environment | Tech. Assist. | Multi-Asset | DCCNR | GCF | Ministry | No |  | National Adaptation Plan | Review and Update the NAP | Ongoing | 1500000 | USD |  |  | X |  | GCF | 2343.75
45 | ENV-13 | Yes | Yes | Environment | New | Coastal Protection | DOID |  | Condition | No | Coastal Protection Program | Renewal of Seawalls - Ch3060 - rear of Aiwo Hotel (66 Metres) | Construction renewal of existing Seawalls at the rear of Aiwo Hotel | Planned | 396000 | AUD |  | X | X |  |  | 396 | 2026 - 2028 |  |  | DS | Nauru Coastal Assessment Survey 2023
46 | ENV-14 | Yes | No | Environment | New | Coastal Protection | DOID |  | Condition | No | Coastal Protection Program | Renewal of Seawalls - Ch4670 - short pronounced seawall immediately north of new Nauru port (82 Metres) | Construction renewal of existing Seawalls immediately North of Nauru Port | Planned | 492000 | AUD |  | X | X |  |  | 492 | 2026 - 2028 |  |  | DS | Nauru Coastal Assessment Survey 2023
47 | ENV-15 | Yes | No | Environment | New | Coastal Protection | DOID |  | Condition | No | Coastal Protection Program | Renewal of Seawalls - Ch4770 - long seawall spanning north from new Nauru port (386 Metres) | Construction renewal of existing Seawalls North of the Nauru Port | Planned | 2316000 | AUD |  | X | X |  |  | 2316 | 2026 - 2030 |  |  | DS | Nauru Coastal Assessment Survey 2023
48 | ENV-16 | Yes | No | Environment | New | Coastal Protection | DOID |  | Condition | No | Coastal Protection Program | Renewal of Seawalls - Ch3060 - Ch14810 - Menen Hotel (414 Metres) | Construction renewal of existing Seawalls near the Menen Hotel | Planned | 2484000 | AUD |  | X | X |  |  | 2484 | 2026 - 2030 |  |  | DS | Nauru Coastal Assessment Survey 2023
49 | ENV-17 | Yes | Yes | Environment | New | Coastal Protection | DOID |  | Condition | No | Coastal Protection Program | Construction of Seawalls (Various Locations) | Construction of new Seawalls - ANETAN (59 Metres) | Appraising | 324500 | AUD |  | X | X |  |  | 324.5 | 2024 - 2026 |  |  | DS | Nauru Coastal Assessment Survey 2023
50 | ENV-18 | Yes | Yes | Environment | New | Coastal Protection | DOID |  | Condition | No | Coastal Protection Program | Construction of Seawalls (Various Locations) | Construction of new Seawalls - ANABAR (27 Metres) | Appraising | 148500 | AUD |  | X | X |  |  | 148.5 | 2024 - 2026 |  |  | DS | Nauru Coastal Assessment Survey 2023
51 | ENV-19 | Yes | No | Environment | New | Coastal Protection | DOID |  | Condition | No | Coastal Protection Program | Construction of Seawalls (Various Locations) | Construction of new Seawalls - ANIBARE (40 Metres) | Appraising | 220000 | AUD |  | X | X |  |  | 220 | 2024 - 2026 |  |  | DS | Nauru Coastal Assessment Survey 2023
52 | ENV-27 | Yes | No | Environment | Maintenance | Coastal Protection | DOID |  | Condition | No | Coastal Protection Program | Repairs to Existing Seawalls (riprap) | To Inspect the condition of the 11 existing ripraps around the island and perform maintenance/repairs where necessary. | Planned | 770000 | AUD |  |  | X |  |  | 770 | 2024-2025
53 | ENV-25 | Yes | No | Environment | Maintenance | Coastal Protection | DOID |  | Condition | Yes | Coastal Protection Program | - | To Inspect the condition of the 11 existing ripraps around the island and perform maintenance/repairs where necessary. | Planned | 2000000 | AUD |  |  | X |  |  | 2000 | 2028-2030+
54 | ENV-23 | Yes | No | Environment | Upgrade | Coastal Protection | NPF |  | Ministry | No |  | New Seawall Behind the Central Police Station | Land is eroding and in the future may take the Police Station to its feet, so the back needs to be back filled and a seawall built. If eroding is left unattened too , may cause major distruptions In tne near future | Planned | 400000 | AUD |  | X |  |  |  | 400
55 | ENV-20 | Yes | Yes | Environment | Tech. Assist. | Other Assets | NRC |  | Ministry | No | High Ground Initiatives Program | Topside Land Clearing and HGI Div Establishment | To develop a holistic plan for new infrastructure at Topside, land development at topside and establishment of new HGI Division. | Budgeted | 1600000 | AUD |  | X |  |  |  | 1600 | 2023 |  | $1.6 million is provided to Nauru Rehabilitation Corporation (NRC) to support further land clearing at Top Side for a cemetery site. | GF | 2022-23 Budget
56 | ENV-21 | Yes | Yes | Environment | Upgrade | Other Assets | NRC | GCF | Importance | Yes | High Ground Initiatives Program | - | Higher Ground Initiatives to Mitigate against Climate and Environmental degradation – the fight against climate change continues as government considers options to relocate key infrastructure and housing to higher locations, as protection against rising sea levels. | Ongoing | 100000000 | AUD |  |  | X |  |  | 100000
57 | ENV-22 | Yes | Yes | Environment | Tech. Assist. | Other Assets | NRC |  | Ministry | No | High Ground Initiatives Program | HGI Master Plan for Agriculture | 2022-23 funding for the design of a whole island master plan for agriculture and natural areas and to commence tenure consultations | Ongoing | 1700000 | AUD |  | X |  |  |  | 1700 | 2023 |  | $1.7 million available for High Ground Initiatives project. Funding will be for the design of a whole island master plan for agriculture and natural areas and to commence tenure consultations
58 | ENV-24 | Yes | Yes | Environment | Upgrade | Reclamation | NRC |  | Importance | No | Land Reclamation | Nursery Plant Site Development | Development of nursery to provide key materials for land rehabilitation. Project includesland reclamation and development of greenhouse, mulcher, mixer tank, water tanker and tank. 0.5 Ha | Appraising | 70000 | AUD | X |  | X |  |  | 70 | 2024
59 | HEA-12 | Yes | No | Health | New | Buildings | DOH | Public Health | Ministry | No | Health Sector Support Program | New Wellness Centers (Yaren, Anibar & NPHC) | Construction of three new health facilities for primary health care servcies | Budgeted | 7500000 | AUD |  |  | X |  | Australia DFAT | 7500 | 2024-2026 |  | Funding to be part of Australia DFAT health sector support program | AOC
60 | HEA-13 | Yes | No | Health | New | Buildings | DOH | Medical Servcies | Ministry | No | Health Sector Support Program | New Pharmacy and Medical Supplies Warehouse | Construction of a purpose built pharmacy and medical supplies warehouse at RONH site. | Budgeted | 2500000 | AUD |  |  | X |  | Australia DFAT | 2500 | 2024-2025 |  | Funding to be part of Australia DFAT health sector support program | AOC
61 | HEA-14 | Yes | No | Health | New | Buildings | DOH | Medical Services | Ministry | No |  | New Renal Dialysis Unit Building | Relocate and construct new renal dialysis unit | Appraising | 2000000 | AUD |  |  | X |  | Korea & India | 2000 | 2024-2025 |  | Grant application submitted to Korea, request to India for equipment | AOC
62 | HEA-15 | No |  | Health | Renewal | Building | DOH | Medical Services | Ministry | No |  | Hospital Security Fence and Parking Area | Define RONH site, secure property and control car parking to allow emergecy access. | Budgeted | 100000 | AUD | X |  |  |  | GON AoP 23/24 | 100 | 2023-2024 |  | Proposing to implement as part of current workplan | AOC
63 | HEA-16 | No |  | Health | Upgrade | Building | DOH | Medical Services | Ministry | No |  | OHS Repair to GOPD/ER/CCU Flooring | Repair and replacemnet of current flooring | Budgeted | 300000 | AUD | X |  |  |  | GON AOP 23/24 | 300 | 2023-2024 |  | Proposing to implement as part of current workplan | AOC
64 | HEA-17 | Yes | No | Health | New | Buildings | DOH |  | Ministry | No |  | New Disability Friendly Training Institute | New disability friendly institute for training health professionals and conduct nursing award programs under the Nauru Health Professionals Training Institute. | Ongoing | 300000 | AUD |  | X |  |  | GON | 300 | 2023 | 0% |  | AOC | 2022-23 Budget
65 | HEA-18 | Yes | No | Health | Renewal | Buildings | DOH | Public Health | Importance | No |  | Redevelopment of Naoero Public Health Centre | Reconstuction buildings lost to fire in December 2022 and extend range of servcies offered on site | Planned | 53000000 | AUD |  | X | X |  | Multiple Donor and GON | 53000 | 2025-2030 |  | Current master planning at pre-design phase | AOC
66 | HEA-19 | Yes | No | Health | Renewal | Buildings | DOH | Medical Services | Importance | No |  | Redevelopment of RoN Hospital | Redevelopment of RONH at current site, reorientation of hospital to improve functionality | Planned | 93000000 | AUD |  | X | X |  | Multiple Donor and GON | 93000 | 2025-2030 |  | Current master planning at pre-design phase | AOC
67 | HEA-20 | No |  | Health | New | Stormwater | DOH | Medical Services | Ministry | No |  | RONH Drainage Upgrade | Upgrading of drainage system at RONH | Planned | 500000 | AUD |  | X |  |  | GON | 500 | 2023-2024 |  | Initial discussions with GON to access emergency response funding | AOC
68 | HEA-11 | No |  | Health | Renewal | Buildings | DOS |  | Ministry | No | Sports Complex - phase 2 | Refurbishment of RFS Building | Revamping of the RFS building to accommodate new office, recreation facilities and conference rooms. | Ongoing | 200000 | AUD |  | X |  |  |  | 200 | 2023 | 70% |  | GF | 2022-23 Budget
69 | ICT-14 | No |  | ICT | Upgrade | Specialty Equipment | CENPAC |  | Ministry | No |  | Equipment to Improve Internet Coverage | 3x 50m communication flight towers, 2 Fibre Optic Cable Splicer, 15 Fibre Optic Transceivers, 10 Cisco Port Switches with accessories | Ongoing | 250000 | AUD |  |  | X |  | Taiwan (ROC) | 250 | 2023 |  | Taiwan will provide AUD $248,227 to assist CENPAC in purchasing much needed resources for the betterment of internet coverage | GF | 2022-23 Budget
70 | ICT-11 | No |  | ICT | New | Towers and ICT | DOM |  | Ministry | No |  | Pay TV Infrastructure Implementation Supporting documents | To install a 12-channel pay TV structure in Nauru to provide the general public with more options for sourcing news and entertainment. Training and development of local staff to operate this expanded service is also included. | Planned | 500000 | AUD |  |  | X |  |  | 500 | 2025 |  | This is not currently being discussed with Donor partners. On hold by instruction from Parliament | GF | Book1
71 | ICT-12 | Yes | No | ICT | Purchase | Towers and ICT | DOM |  | Ministry | No |  | Sustainable Power Supply for Media Building | Purchasing and Installing solar panels for media building for steady power flow | Planned | 200000 | AUD |  |  | X |  |  | 200 | 2025 |  |  | KD
72 | ICT-13 | No |  | ICT | New | Towers and ICT | DOM |  | Ministry | Yes | East Micronesia Undersea Cable | - | Provide undersea cable to connect Nauru to Pohnpei to provide international internet connectivity | Ongoing |  | AUD |  |  | X |  | AIFFP |  | 2024
73 | ICT-15 | No |  | ICT | New | Towers and ICT | DOM |  | Ministry | No |  | Construction of Secure Area for High Value Equipment | secure a designated and secure site for the permanent installation of satellite dishes and other valauble infrastructure. | Budgeted | 50000 | AUD |  | X |  |  |  | 50 | 2023 |  | project awaiting funding to be released | KD
74 | ICT-16 | Yes | No | ICT | Maintenance | Towers and ICT | DOM |  | Ministry | No |  | High Value Equipment Corrective Repairs | Repair and Maintenance of high value equipment focusing on Transmission towers, transmission equipment and high end editing equipment. | Planned | 150000 | AUD |  |  | X |  |  | 150 | 2024 |  | feasibility study to be done to determine the total cost of repair and maintenance costs on a yearly basis. | KD
75 | IND-11 | No |  | Industry | Renewal | Other Assets | CIE | CIE - DEMA | Ministry | No |  | Pilot Disposal of Legacy Asbestos Waste | To dispose of 5 containers of asbestos waste in deep sea waters within our EEZ. | Appraising | 50000 | AUD |  |  | X |  | ADB | 50 | 2024 |  | 21-001, M | GF | Book1
76 | JUS-14 | No |  | Justice | Upgrade | Buildings | DOJ |  | Ministry | No |  | Upgrade of Central Court |  | Planned |  | AUD |  |  | X |  |  | 0 | 2026
77 | JUS-11 | Yes | No | Justice | Upgrade | Buildings | NPF |  | Ministry | No | Nauru Police - Repairs and Upgrade of buildings | Upgrading the Central Police Station | To repair the current Central Police Station as it has become an OHS issue for employees. The current building is urgent need for ceiling changes, painting, major repair of the current roofing, as the architectures of the roofing is causing major ceiling flooding and electrical faults. Fearing if left unattended may cause fire works. | Planned | 200000 | AUD |  | X |  |  |  | 200
78 | JUS-12 | Yes | No | Justice | Purchase | Specialty Equipment | NPF |  | Ministry | No |  | Maritime Police Unit | There is a need to repair and maintain daily operations of Maritime fleets, hence this project is highly anticipated. this will also include the purchase of a towing vehicle, that currently hiring of a heavy duty truck to tow the boats is very expensive, therefore a towing vehicle is urgently needed as well as a permanant office for Police Maritime and Security (~$100,000p.a) | Planned | 500000 | AUD |  | X |  |  |  | 500 |  |  | (~$100,000p.a)
79 | JUS-13 | Yes | No | Justice | Upgrade | Buildings | NPF |  | Ministry | No | Nauru Police - Repairs and Upgrade of buildings | Upgrading the Police Training College | To repair the current state of the current Police Training Cente, as the actual building is at the stage of collapse and has become a major OHS issue for employees. The current building is over 20 years old, the current buidling is in urgent need for major repairs such as, change of walls, painting, ceiling replacments, electrical works, water capturing system and tank, as well as the Police Gym | Planned | 500000 | AUD |  | X |  |  |  | 500
80 | LAN-13 | Yes | No | Land | Renewal | Sealed Roads | DOID |  | Condition | Yes | Capital Repairs to Sealed Roads | - | Resealing and Repairs to Existing Roads | Planned | 14000000 | AUD |  | X | X |  |  | 14000 | 2025-2030
81 | LAN-14 | Yes | Yes | Land | Upgrade | Sealed Roads | DOID |  | Importance | No |  | Barrier Railing – Airport Ring Road | Renewal and Construction of 820LM of new Armco Barrier to Airport ring road. | Planned | 529000 | AUD | [5 empty] | 529 | 2026 |  |  | GF | Book1
82 | LAN-15 | Yes | No | Land | Renewal | Sealed Roads | DOID |  | Importance | No | Capital Repairs to Sealed Roads | Rehabilitation of Embassy Hill Road and Access Roads | Capital repairs to base pavement, surface seal and drainage of approximately 2.5 km road length on Embassy hill and two access roads | Planned | 2000000 | AUD | [5 empty] | 2000 |  |  |  | SO
83 | LAN-16 | Yes | No | Land | Renewal | Sealed Roads | DOID |  | Condition | No | Capital Repairs to Sealed Roads | Rehabilitation of Boe School Access Road | Capital repairs to base pavement, surface seal and drainage of approximately 315 m road length providing access to Boe Infant School | Planned | 250000 | AUD | [5 empty] | 250 |  |  |  | SO
84 | LAN-17 | Yes | No | Land | Renewal | Sealed Roads | DOID |  | Condition | No | Capital Repairs to Sealed Roads | Improving Drainage on Ring Road | Capital repairs to the drainage system, including repairs and/or capacity increase of about 25 soak pits and addition of drain pipes to soak pits where capacity of soak areas is limited | Planned | 750000 | AUD | [5 empty] | 750 |  |  |  | SO
85 | LAN-18 | Yes | No | Land | Maintenance | Sealed Roads | DOID |  | Condition | No | Capital Repairs to Sealed Roads | Capital Repairs to Roadside Curbs and Drainage | To inspect the condition of roadside curbs, driveways and gutters around the ring road and to perform repairs/renewal where needed | Planned | 250000 | AUD |  | X | X |  |  | 250 | 2024-2025
86 | LAN-19 | No |  | Land | Maintenance | Sealed Roads | DOID |  | Condition | No | Road Maintenance | Preventive Road Maintenance Capacity | Road Maintenance program inclusive of Development, Training, Equipment & Materials to establish a road maintenance team. Implementation of a Asset Management & Maintenance regime focussed on preventative maintenance and Adhoc repairs. | Appraising | 310000 | AUD |  |  | X |  |  | 310 | 2024 |  | 63-006, M | GF | Book1
87 | LAN-20 | No |  | Land | Tech. Assist. | Other Assets | DOID |  | Condition | No |  | Asset Management Specialist | Technical assistance in the establishment of an Asset management framework and maintenance plans for public infrastructure such as Roads, Buildings, Seawalls and related asset components | Appraising | 300000 | AUD |  |  | X |  |  | 300 | 2024 |  | 63-008, ? | GF | Book1
88 | LAN-21 | No |  | Land | Renewal | Sealed Roads | DOID |  | Condition | No |  | Road Section Renewal – Airport Crossing | The re-construction of a 1700m section of public road running from the main ring road in the Aiwo district. | Planned | 1785000 | AUD | [5 empty] | 1785 | 2026 |  |  | GF | Book1
89 | LAN-26 | No |  | Land | Maintenance | Sealed Roads | DOID |  | Condition | No | Road Maintenance | Line Marking Renewal – Nauru Rong Road | The Repainting, of the line markings to the ring road. Approximate Road Length – 22.15km | Appraising | 271000 | AUD |  | X |  |  |  | 271 | 2025 |  | 63-007, M | GF | Book1
90 | LAN-11 | No |  | Land | New | Specialty Equipment | DOT |  | Ministry | No |  | Mobile Vehicle Inspection Unit | To provide a modern inspection unit, equipped with the latest vehicle testing equipment. This unit will be able to assist the VRID office to accurately inspect and assess the safety of vehicles. | Appraising | 560000 | AUD |  | X | X |  | tbd | 560 | 2025 |  | 91-002, H | GF | Book1
91 | LAN-12 | No |  | Land | New | Specialty Equipment | DOT |  | Ministry | No |  | Nauru Electric Vehicles Charging Facility | To setup electric vehicle charging station in dedicated locations to facilitate the charging of electric vehicles/electric bikes | Planned | 3000000 | AUD |  |  | X |  |  | 3000
92 | LAN-22 | No |  | Land | Purchase | Motor Vehicles | DOT |  | Ministry | No |  | Number Plate Embossing Machinery | To set up a number plate embossing machinery in Nauru to enable the VRID office to provide number plates efficiently, and at reduced costs. | Appraising | 93000 | AUD |  | X | X |  | tbd | 93 | 2024 |  | 91-003, ? | GF | Book1
93 | LAN-23 | No |  | Land | New | Buildings | DOT |  | Ministry | No |  | VRID Office Construction | To relocate the Vehicle Registration and Insurance Division (VRID) Office to a location where it is in appropriate distance to NRO, has better internet connectivity and parking facility. BR1- when unit arrives the supplier requires it to be accompanied by a technician, hence the travel costs. Unsure about ongoing software licensing costs, think most of it is just mechanical. Could be some digital components and think cost would be minimal. | Planned | 104000 | AUD |  | X | X |  |  | 104 | 2026 |  |  | GF | Book1
94 | LAN-24 | No |  | Land | Purchase | Specialty Vehicles | DOT |  | Ministry | No |  | Nauru Electric/Hybrid Bus Public Transportation | By 1st qtr of 2024, Nauru will have its first electric bus for public transportation as a pilot project. DOT requires 8 buses dedicated for public transportation. As there will be a electric charging station,DOT would like to increase the electric/bybrid bus fleet. | Planned | 1000000 | AUD |  |  | X |  |  | 1000
95 | LAN-25 | No |  | Land | Tech. Assist. | Specialty Vehicles | DOT |  | Ministry | No |  | Nauru Light Rail Feasibility Study | In the long term prespective, in order to reduce the expense met due to the import of the fuels for vehicles and its maintenance and to provide a reliable public transportation. The DOT is proposing to conduct a feasibility study on a light rail project. | Planned | 1000000 | AUD |  |  | X |  |  | 1000
96 | LAN-28 | No |  | Land | New | Buildings | DOT |  | Ministry | No |  | Nauru Land Transport Authority Building | To set up a multi discipline functioning building which undertakes vehicle registration, vehicle inspection, number plate embsossing, Drivers licence, vehicle servicing garage and Nauru Public Transport Bus parking Bay. | Planned | 5000000 | AUD |  | X | X |  |  | 5000
97 | LAN-29 | No |  | Land | Upgrade | Sealed Roads | NRC |  | Ministry | No | Land Reclamation | Fire Hazard Road Development | Tank farm Vital Project | Appraising | 400000 | AUD |  |  |  | X |  | 400
98 | PUB-22 | Yes | No | PublicBuilding | Upgrade | Buildings | PSA |  | Ministry | No |  | PSA Office Development and Renovation | Acquire new office space, build reception area, meeting room and surveyors room and renovation of other office space | Planned | 20000 | AUD |  | X |  |  |  | 20 | 2023-2024 |  |  | PSA
99 | MAR-11 | No |  | Maritime | Purchase | Boats and Vessels | NMPA |  | Ministry | No | Mooring System Restoration | Hire of Tugboats for Phosphate and Fuel Ships | Hire tugs (1 year) to assist berthing and mooring ships while mooring system is restored back to operational status. | Appraising | 3194000 | AUD |  | X |  |  |  | 3194 | 2024 |  |  | GF | Book1
100 | MAR-12 | Yes | Yes | Maritime | New | Specialty Equipment | NMPA |  | Ministry | No | Sustainable and Climate-Resilient Connectivity Project | Heavy Lifting Solution - Crane | Heavy Lifting Solution - Crane for new tugboat (donated through JICS) as part of Nauru Port Development Project. | Appraising | 4500000 | AUD |  | X | X |  |  | 4500 | 2024 |  |  | GF | Book1
101 | MAR-13 | No |  | Maritime | Upgrade | Multi-Asset | NMPA |  | Ministry | Yes | Sustainable and Climate-Resilient Connectivity Project | - | Allowance for remaining tasks not yet scoped | Ongoing |  | AUD |  | X | X |  | ADB, GON |  |  |  | Total fund USD$62.3m approved 2018 | GF | Dev. Fund Projection 22-23
102 | MAR-14 | No |  | Maritime | New | Multi-Asset | NMPA |  | Ministry | No | Sustainable and Climate-Resilient Connectivity Project | Port Revelopment Project |  | Ongoing | 2100000 | AUD |  | X |  |  |  | 2100 | 2024 |  | $2.1 million to support the Port Redevelopment Project | GF | 2022-23 Budget
103 | MAR-15 | No |  | Maritime | New | Buildings | NMPA |  | Ministry | No | Sustainable and Climate-Resilient Connectivity Project | NMPA Maintenance Capacity Training | Maintenance and Capacity Training for NMPA Employees | Planned | 4000000 | AUD |  | X | X |  |  | 4000 |  |  |  | NMPA
104 | MAR-16 | No |  | Maritime | Renewal | Wharfs and Jetties | NMPA |  | Ministry | No | Mooring System Restoration | Repair of Mooring System (Ronphos) | Funding was provided by Australia to scope options for replacement or repair- this work was not completed. NMPA is the lead on the project. It would be cheaper to replace this with a rotainer system but Ronphos wishes to retain this and the cantilever system | Ongoing | 6800000 | AUD | X |  |  |  |  | 6800 | 2022 |  | PAN-E3 | GF | 2022-23 Budget
105 | MAR-17 | No |  | Maritime | Tech. Assist. | Wharfs and Jetties | NMPA |  | Ministry | No |  | Community Servoce Obligation (CSO) Tariff Review | CSO under Public Enterpises Act 2019 to cover change in tariff at port. Additional revenue to fund infrastructure. | Appraising | 1690000 | AUD |  | X |  |  |  | 1690 | 2024 |  |  | GF | Book1
106 | PUB-15 | No |  | PublicBuilding | New | Buildings | DOID |  | Ministry | No | Community Housing | Nauru Community Housing | Construction & Remediation of new and existing housing for the community | Ongoing | 7000000 | AUD |  | X |  |  |  | 7000 | 2023 |  | Ongoing program | DS | 23/24 Budget
107 | PUB-16 | No |  | PublicBuilding | New | Housing | DOID |  | Ministry | No | Smart Homes Program | Container Homes Projects | 20 Homes Container | Ongoing | 1030684 | AUD |  | X |  |  | PAD | 1030.684 | 2023 |  | Challenges with the completion, due to lack of appropriately skilled resources
108 | PUB-19 | Yes | Yes | PublicBuilding | New | Housing | DOID |  | Ministry | No | Smart Homes Program | Smart House Project 2023/2025 | 18 Smart House | Ongoing | 2354969 | AUD |  | X |  |  | PAD | 2354.969 | 2023 |  | Challenges with the completion, due to lack of appropriately skilled resources
109 | PUB-20 | No |  | PublicBuilding | New | Housing | DOID |  | Ministry | No | Smart Homes Program | Pilot Smart Housing Projects | 4 Pilot Smart Smart House | Ongoing | 231554 | AUD |  | X |  |  | PAD | 231.554 | 2023 |  | Procured all Materials from EHC awaiting shipment arrivals
110 | PUB-12 | No |  | PublicBuilding | New | Building | DOM |  | Ministry | No |  | New Media Conference room | Reconstruction of Media conference room | Ongoing | 45000 | AUD |  | X |  |  |  | 45 | 2023-2024 | 20% | Construction to Begin in March 2024 | KD
111 | PUB-21 | No |  | PublicBuilding | New | Building | DOM |  | Ministry | No |  | New Music Recording Studio | Reconstuction of Music recording studio to be located at the main building | Ongoing | 30000 | AUD |  | X |  |  |  | 30 | 2023-2024 | 20% | construction to begin in March 2024 | KD
112 | PUB-13 | Yes | No | PublicBuilding | Upgrade | Buildings | NFMRA |  | Ministry | No |  | Refurbishment of Aquaculture Holding Centre |  | Planned | 1000000 | AUD |  |  | X |  |  | 1000 | 2024
113 | PUB-14 | No |  | PublicBuilding | Renewal | Heavy Equipment | NMPA |  | Ministry | No |  | Replacement of Fortlift | 2.5t forklift has reached end of life and required replacement | Planned | 40000 | USD |  | X | X |  | JICS | 62.5 |  |  |  | NMPA
114 | PUB-18 | No |  | PublicBuilding | New | Housing | NMPA |  | Ministry | No | Sustainable and Climate-Resilient Connectivity Project | Relocation of Housing in Red Zone | Funding for the leasing, repairs and maintenance of 38 houses for temporary accommodation as part of relocation plan. | Appraising | 1240000 | AUD |  |  | X |  | ADB | 1240 | 2024 |  |  | GF | Book1
115 | PUB-11 | Yes | No | PublicBuilding | Renewal | Buildings | PSA |  | Condition | No |  | Reconstruction of Internal Affairs Buildings (Mennen Hill) | Reconstruction of internal affairs buildings located on Mennen Hill, including child protection and counselling, tourism office, domestic violence shelter, Nauru Cultural center and Youth Affairs Services Buidlings | Planned | 1300000 | AUD |  |  | X |  |  | 1300 |  |  |  | SO
116 | PUB-17 | Yes | No | PublicBuilding | Tech. Assist. | Buildings | PSA |  | Ministry | No |  | Master Plan for Government Building (Consolidation) | Master plan for redevelopment of the main admin building, possibly relocation to high ground, and green energy. Also consolidation of government buildings into one area. | Planned | 400000 | AUD |  | X |  |  |  | 400 |  |  |  | MD
117 | SPO-11 | No |  | Recreation | New | Other Assets | DOS | DOE | Ministry | No | Sporting Facilities in All Schools | Outdoor Sports Field | Lease new land spaces to build sporting fields near schools | Planned | 4000000 | AUD |  |  | X |  |  | 4000
118 | SPO-12 | Yes | Yes | Recreation | New | Multi-Asset | DOS | NRC | Importance | Yes | Micronesian Games 2026 Infrastructures Program | - |  | Planned | 14500000 | AUD |  |  | X |  |  | 14500 | 2023
119 | SPO-13 | No |  | Recreation | New | Other Assets | DOS | NRC | Importance | No | Micronesian Games 2026 Infrastructures | Track and Field Facilities | Build New Track & Field to cater Micronesian Games 2026 | Planned | 5500000 | AUD |  |  | X |  |  | 5500
120 | SPO-14 | Yes | Yes | Recreation | New | Buildings | DOS | NRC | Importance | No | Micronesian Games 2026 Infrastructures | Grandstand Stadium with Indoor Sport Hall | Seating embarkment view, office spaces, VIP arena, change room, toilets & indoor sports | Planned | 8000000 | AUD |  |  | X |  |  | 8000
121 | SPO-15 | Yes | Yes | Recreation | New | Buildings | DOS | NRC | Importance | No | Micronesian Games 2026 Infrastructures | Mini Sports Halls | Two new sports hall to dedicate building to sports like Boxing, Wrestling, Judo, Powerlifting | Planned | 1500000 | AUD |  |  | X |  |  | 1500
122 | SPO-16 | Yes | Yes | Recreation | New | Buildings | DOS | NRC | Ministry | No | Micronesian Games 2026 Infrastructures | High Performance Center | Elite athlete development pathway traininig center | Planned | 750000 | AUD |  |  | X |  |  | 750
123 | SPO-17 | Yes | Yes | Recreation | New | Reclamation | DOS | NRC | Importance | No | Micronesian Games 2026 Infrastructures | Land Site Preparation and Access Road | Contracting expertise Rehab corperation in doing the land leveling project | Planned | 4100000 | AUD |  |  | X |  |  | 4100
124 | SPO-18 | Yes | Yes | Recreation | Upgrade | Specialty Equipment | DOS | NRC | Ministry | No | Micronesian Games 2026 Infrastructures | Renovation of Existing Sport Courts | Tennis courts, Basketball & Volleyball Courts | Planned | 1000000 | AUD |  |  | X |  |  | 1000
125 | SPO-19 | Yes | No | Recreation | New | Specialty Equipment | DOS | NRC | Importance | No | Micronesian Games 2026 Infrastructures | Sporting Equipments and Accessories | Equipments & assets for the Games | Planned | 2500000 | AUD |  |  | X |  |  | 2500
126 | SPO-20 | Yes | Yes | Recreation | New | Buildings | DOS | NRC | Importance | No | Micronesian Games 2026 Infrastructures | Games Village | Accommodation games village to assist with the limited accommodations on island | Planned | 6500000 | AUD |  |  | X |  |  | 6500
127 | SPO-21 | No |  | Recreation | New | Multi-Asset | DOS | DOE | Ministry | Yes | Sporting Facilities in All Schools |  |  | Planned |  | AUD |  |  | X |  |  | 0 | 2026
128 | SPO-22 | No |  | Recreation | New | Buildings | DOS | DOE | Ministry | No | Sporting Facilities in All Schools | Overhead Sports Hall | Build new overhead sports hall | Planned | 6000000 | AUD |  |  | X |  |  | 6000
129 | SWA-14 | No |  | Waste | New | Multi-Asset | DCCNR | NRC/ADB | Importance | No |  | Compost Facility | Construction of compost facility and resource recovery centre | Ongoing |  | AUD |  |  | X |  | ADB |  |  |  |  | Mark Hiram
130 | SWA-13 | No |  | Waste | New | Buildings | DOT |  | Ministry | No |  | Nauru Vehicle Recycling Facility | to shredd old derelict vehicles and to process the scrap for shipment, this project involves multiple entities like DOT,DOID,DEMA,CCNR and NRC | Planned | 7000000 | AUD |  |  | X |  |  | 7000
131 | SWA-11 | No |  | Waste | New | Buildings | NRC |  | Ministry | No |  | Waste recycling centre | Processing centre for recyclables, includes cars, scrap metal, plastic, white goods, e-waste, tyres, hazardous waste (inc asbestos) | Planned |  | AUD |  |  | X |  | ADB | 0
132 | SWA-12 | No |  | Waste | Renewal | Unknown (tbd) | NRC |  | Ministry | No |  | Redevelopment of Landfill Site | Redesign and redeveopment of existing landfill site to mitigate adverse environmental, health and safety impacts, including leachate capture to prevent ground water contamination | Planned | 5000000 | AUD |  |  | X |  | ADB/Japan | 5000 |  |  |  | Mark Hiram
133 | WAS-15 | No |  | WaterSewer | New | Septic Tanks | CIE | CIE - DEMA | Ministry | No |  | Provision of Twin Chamber Household Septic Systems | To install twin chamber septic tanks (30) at the household level to minimize the contamination of brackish water and to help address the negative impacts on public and environmental health. | Appraising | 80000 | AUD |  |  | X |  | ADB | 80 | 2024 |  | 21-002, H | GF | Book1
134 | WAS-11 | No |  | WaterSewer | New | Water Treatment | DCCNR | DCCNR - Energy | Ministry | No |  | Solar Water RO-Purifier System Project | The proposed project is to provide a solar-based RO system drinking water solution for the hospital. There will be a drinking water kiosk kept outside the hospital that will help the hospital and the community outside get free drinking water, along with water for normal hospital use. The project is funded by the International Solar Alliance (ISA) with a grant of 50,000 US$. | Appraising | 50000 | USD |  | X | X |  | ISA,GON | 78.125 | 2024 |  | 22-003, M | GF | Book1
135 | WAS-12 | No |  | WaterSewer | Upgrade | Sewerage Treatment | DCCNR | NUC | Ministry | No |  | Development of a new Sewage Treatment Plant | Design and Development of a sewage treatment plant, with adequate capacity to accept, treat and discharge sewage waste pumped from all public and private septic tanks | Planned | 5000000 | AUD | [5 empty] | 5000 |  |  |  | SO
136 | WAS-14 | Yes | No | WaterSewer | Tech. Assist. | Multi-Asset | DCCNR | NUC, DOF | Importance | No | Nauru Sustainable Urban Development Project | Nauru Sustainable Urban Development Project (Design) | Identify opportunities to improve water supply, sanitation and solid waste management on Nauru | Ongoing | 2000000 | USD |  |  | X |  | ADB | 3125 | 2022-2024 | 60% |  | GF
137 | WAS-16 | Yes | No | WaterSewer | Upgrade | Multi-Asset | DCCNR | NUC, DOF | Importance | Yes | Nauru Sustainable Urban Development Project |  | Implement improvements in water supply, sanitation and solid waste management from Master Plan | Appraising | 38500000 | USD |  |  | X |  | ADB | 60156.25 | 2022-2026 |  | For FY 2022-23, ADB is expecting to contribute $1.5 million in-kind assistance for this project. | GF | Dev. Fund Projection 22-23
138 | WAS-17 | Yes | No | WaterSewer | New | Multi-Asset | DCCNR | NUC/ADB | Importance | No | Nauru Sustainable Urban Development Project | Water Reticulation to Households | Reticulation and Reservoirs for households | Ongoing |  | AUD |  |  | X |  | ADB |  |  |  |  | Mark Hiram
139 | WAS-18 | Yes | Yes | WaterSewer | New | Storage Tanks | DCCNR | DCCNR - Water | Ministry | No |  | Provision of Household Water Storage Tanks | Securing Nauru’s access to water by augmenting household water storage capacity and improving supply side constraints by constructing 10,000L water tanks to households (50). | Appraising | 200000 | AUD |  | X |  |  |  | 200 | 2024 |  | 22-002, L | GF | Book1
140 | WAS-13 | Yes | No | WaterSewer | New | Reservoirs | NUC-W | NUC | Ministry | No |  | Water Storage Tank Upgrade | Expanding Storage Capacity. Rehab 3 million L water storage tank and 2 x 300,000 L water treatment tanks for B-13 site - materials on island - need a new contractor | Planned | 350000 | AUD | X | X |  |  | NUC | 350 | 2024 |  |  | Mark Hiram
141 | WAS-19 | Yes | No | WaterSewer | New | Pipelines | NUC-W | PMU, DCCNR | Ministry | No | Nauru Sustainable Urban Development Project | Water Supply Pipeline (NSUDP) | Reticulation and Reservoirs for households | Appraising | 37400000 | AUD |  |  | X |  | ADB | 37400 | 2025 |  | Feasibilty Studeis completed, NUC as IA | Mark Hiram | PMU
142 | WAS-20 | Yes | No | WaterSewer | New | Other Assets | NUC-W | PMU | Ministry | No | Nauru Sustainable Urban Development Project | Sanitation Upgrade (NSUDP) | System for treatment of sludge from septic tanks to produce nitrogen rich compost for land reclamation | Appraising | 28000000 | AUD |  |  | X |  | ADB | 28000 | 2025 |  | Feasibilty Studeis completed, NUC as IA | Mark Hiram | PMU
143 | WAS-21 | Yes | No | WaterSewer | Upgrade | Other Assets | NUC-W | NUC | Ministry | No |  | SMARTEN RO Project | Establishment of Water Production Facility at Meneng Site | Ongoing | 100000 | AUD | X |  | X |  | NUC | 100 | 2025 |  |  | Mark Hiram
144 | WAS-22 | No |  | WaterSewer | New | Other Assets | NUC-W | NUC | Ministry | No |  | Water Office Project | Office to accomdate water administation and Lab | Ongoing | 100000 | AUD | X |  |  |  | NUC | 100 | 2023 |  |  | Mark Hiram
145 | LAN-30 | Yes | No | Land | New | Other Assets | DEMA |  | Ministry | No |  | Extension of Menen Farm | DEMA is in the process of working with UNDP to access $2m from China's Global Development South South Cooperation Fund to construct the necessary infrastructure to install climate smart agricultural technologies on site | Planned | 2000000 | AUD | X |  |  |  |  | 2000 | 2024 |  | An NPP totalling about $500k to clear and prepare the site has been submitted during the budget process and waiting for feedback from Finance. If this does not come to fruition, then we will have to bank on the $2m to support this activity also. | DS | DEMA
Note on K3: Programs cover many sites, can be recurrent (e.g. Road Resurfacing) and generally relate to R&R of existing assets
Note on V3: For ongoing/budgeted name donor(s). For appraising name likely donor or funding source. If unknown leave blank.
Note on AB3: Source of project information (e.g. name of master plan, study, project list etc)

## Analysis
Row Labels | Count of Status | Count of Status | Column Labels |  |  |  |  | Count of Sector Code | Column Labels
Appraising | 28 | Row Labels | Appraising | Budgeted | Ongoing | Planned | Grand Total | Row Labels | Ongoing | Budgeted | Appraising | Planned | Grand Total
Budgeted | 7 | CENPAC |  |  | 1 |  | 1 | New | 14 | 3 | 15 | 35 | 67
Ongoing | 26 | CIE | 2 |  |  |  | 2 | Upgrade | 5 | 1 | 4 | 21 | 31
Planned | 84 | DCCNR | 3 |  | 4 | 4 | 11 | Renewal | 4 | 2 | 2 | 14 | 22
Grand Total | 145 | DOH | 1 | 4 | 1 | 3 | 9 | Maintenance |  |  | 2 | 4 | 6
|  | DOID | 6 |  | 4 | 13 | 23 | Purchase |  |  | 2 | 5 | 7
|  | DOM |  | 1 | 3 | 3 | 7 | Tech. Assist. | 3 | 1 | 3 | 5 | 12
|  | DOS |  |  | 1 | 12 | 13 | Grand Total | 26 | 7 | 28 | 84 | 145
|  | DOT | 2 |  | 1 | 8 | 11
|  | NMPA | 4 |  | 3 | 2 | 9
|  | NRC | 2 | 1 | 2 | 2 | 7
|  | PSA |  |  |  | 3 | 3 | Row Labels | Ongoing | Budgeted | Appraising | Planned | Grand Total
|  | VEI |  |  | 1 |  | 1 | New | 36.8922 | 10.05 | 78.006 | 95.827 | 220.7752
|  | NUC-E | 3 |  | 2 | 6 | 11 | Upgrade | 140.35 | 0.3 | 40.366 | 17.751 | 198.767
|  | NUC-W | 2 |  | 2 | 1 | 5 | Renewal | 9.057 | 0.34 | 0.072 | 171.75 | 181.219
|  | DOET | 2 | 1 | 1 | 5 | 9 | Maintenance | 0 | 0 | 0.581 | 1.17 | 1.751
|  | NPF |  |  |  | 4 | 4 | Purchase | 0 | 0 | 3.287 | 3.82 | 7.107
|  | TVET | 1 |  |  | 7 | 8 | Tech. Assist. | 5.2 | 1.6 | 2.29 | 71.4 | 80.49
|  | DCA |  |  |  | 2 | 2 | Grand Total | 191.4992 | 12.29 | 124.602 | 361.718 | 690.1092
|  | NES |  |  |  | 6 | 6
|  | DOJ |  |  |  | 1 | 1
|  | NFMRA |  |  |  | 1 | 1
|  | DEMA |  |  |  | 1 | 1
|  | Grand Total | 28 | 7 | 26 | 84 | 145
1000000

## Shortlist
# | Proj. Ref. | MCA.Ref | Sector Code | Project Type | Lead Unit | Program Level Budget Entry? | Program Name | Project /Program Name | Brief Description | Status | Type | Cost Estimate (AU$,000) | Total score | Economy | Social | Environment | Efficiency
118 | SPO-12 | SPO-12 | Recreation | New | DOS | Yes | Micronesian Games 2026 Infrastructures Program | Micronesian Games 2026 Infrastructures Program (MGIP) |  | Planned | 1. MP | 14500 | 86 | 16 | 23 | 24 | 23
120 | SPO-14 | SPO-12 | Recreation | New | DOS | No | Micronesian Games 2026 Infrastructures Program | MGIP: Grandstand Stadium with Indoor Sport Hall | Seating embarkment view, office spaces, VIP arena, change room, toilets & indoor sports | Planned | 1. MP | 8000 | 86 | 16 | 23 | 24 | 23
126 | SPO-20 | SPO-12 | Recreation | New | DOS | No | Micronesian Games 2026 Infrastructures Program | MGIP: Games Village | Accommodation games village to assist with the limited accommodations on island | Planned | 1. MP | 6500 | 86 | 16 | 23 | 24 | 23
21 | EDU-25 | EDU-25 | Education | New | TVET | No |  | New Multipurpose Building for Life Skills | Multi purpose workshop for life skills program training. | Planned | 1. MP | 5000 | 81 | 18 | 23 | 20 | 20
66 | HEA-19 | HEA-19 | Health | Renewal | DOH | No |  | Redevelopment of RoN Hospital | Redevelopment of RONH at current site, reorientation of hospital to improve functionality | Planned | 1. MP | 93000 | 75 | 16 | 19 | 14 | 26
1 | AIR-11 | AIR-11 | Aviation | New | DOT | Yes | Nauru Airport Terminal Redevelopment Program | Nauru Airport Terminal Redevelopment Program | To upgrade the existing terminal with increase in floor space of arrival, departure lounge. Adding new duty free premises, introducing elevated parking lot, introduction of centralised air conditioner. Increasing the solar roofing within the airport premises. A mini sewage treatment plant. | Planned | 1. MP | 20000 | 70 | 20 | 9 | 14 | 27
65 | HEA-18 | HEA-18 | Health | Renewal | DOH | No |  | Redevelopment of Naoero Public Health Centre | Reconstuction buildings lost to fire in December 2022 and extend range of servcies offered on site | Planned | 1. MP | 53000 | 65 | 13 | 19 | 11 | 22
121 | SPO-15 | SPO-12 | Recreation | New | DOS | No | Micronesian Games 2026 Infrastructures Program | MGIP: Mini Sports Halls | Two new sports hall to dedicate building to sports like Boxing, Wrestling, Judo, Powerlifting | Planned | 2. QW | 1500 | 86 | 16 | 23 | 24 | 23
122 | SPO-16 | SPO-12 | Recreation | New | DOS | No | Micronesian Games 2026 Infrastructures Program | MGIP: High Performance Center | Elite athlete development pathway traininig center | Planned | 2. QW | 750 | 86 | 16 | 23 | 24 | 23
123 | SPO-17 | SPO-12 | Recreation | New | DOS | No | Micronesian Games 2026 Infrastructures Program | MGIP: Land Site Preparation and Access Road | Contracting expertise Rehab corperation in doing the land leveling project | Planned | 2. QW | 4100 | 86 | 16 | 23 | 24 | 23
124 | SPO-18 | SPO-12 | Recreation | Upgrade | DOS | No | Micronesian Games 2026 Infrastructures Program | MGIP: Renovation of Existing Sport Courts | Tennis courts, Basketball & Volleyball Courts | Planned | 2. QW | 1000 | 86 | 16 | 23 | 24 | 23
17 | EDU-21 | EDU-21 | Education | Upgrade | TVET | No | Quality Access to Education and Training | Hospitality Kitchen Improvements | To Commercial kitchen Australian standard. | Planned | 2. QW | 3000 | 69 | 19 | 26 | 11 | 13
20 | EDU-24 | EDU-24 | Education | Upgrade | TVET | No | Quality Access to Education and Training | Engineering Industrial Workshop Improvements | Improvement to Engineering workshop | Planned | 2. QW | 3000 | 69 | 12 | 23 | 14 | 20
33 | ENE-14 | ENE-14 | Energy | Upgrade | NUC-E | No | Low Voltage Distribution Line Upgrade | Buada Low Voltage Underground Cable Upgrade | To replace existing undergound cables the whole of Buada District in which have deteriorated and is causing power flunctuations | Planned | 2. QW | 1200 | 69 | 12 | 6 | 21 | 30
38 | ENE-19 | ENE-19 | Energy | Upgrade | NUC-E | No |  | Upgrade 3.3kva Switch Gear at Power Station | Existing switch gear outdated >20years, spares are not available globally | Planned | 2. QW | 1102 | 68 | 22 | 6 | 14 | 26
39 | ENE-20 | ENE-20 | Energy | Upgrade | NUC-E | No |  | Upgrade RMN, RME, and RMS Power Transformers | Existing 2.5MVA TRX are have become insufficent due to forever increasing demand, want to replace with 4.5MVA - urgent project as 1 already down, losing another would lead to load shedding - future proofing | Appraising | 2. QW | 1396 | 68 | 22 | 6 | 14 | 26
37 | ENE-18 | ENE-18 | Energy | Upgrade | NUC-E | No |  | Upgrade Substation at Location Area | Switch exisiting Air Break Switch (ABS) with Ring Main Unit (RMU). Current ABS are deteriorting and in dire need to replace | Planned | 2. QW | 1500 | 67 | 20 | 6 | 14 | 27
78 | JUS-12 | JUS-12 | Justice | Purchase | NPF | No |  | Maritime Police Unit | There is a need to repair and maintain daily operations of Maritime fleets, hence this project is highly anticipated. this will also include the purchase of a towing vehicle, that currently hiring of a heavy duty truck to tow the boats is very expensive, therefore a towing vehicle is urgently needed as well as a permanant office for Police Maritime and Security (~$100,000p.a) | Planned | 2. QW | 500 | 65 | 19 | 12 | 14 | 20
54 | ENV-23 | ENV-23 | Environment | Upgrade | NPF | No |  | New Seawall Behind the Central Police Station | Land is eroding and in the future may take the Police Station to its feet, so the back needs to be back filled and a seawall built. If eroding is left unattened too , may cause major distruptions In tne near future | Planned | 2. QW | 400 | 64 | 9 | 9 | 20 | 26
125 | SPO-19 | SPO-19 | Recreation | New | DOS | No | Micronesian Games 2026 Infrastructures Program | Sporting Equipment and Accessories | Equipments & assets for the Games | Planned | 2. QW | 2500 | 64 | 13 | 23 | 9 | 19
82 | LAN-15 | LAN-15 | Land | Renewal | DOID | No | Capital Repairs to Sealed Road Program | SRRP: Rehab. of Embassy Hill Road and Access Roads | Capital repairs to base pavement, surface seal and drainage of approximately 2.5 km road length on Embassy hill and two access roads | Planned | 2. QW | 2000 | 62 | 9 | 6 | 27 | 20
61 | HEA-14 | HEA-14 | Health | New | DOH | No |  | New Renal Dialysis Unit Building | Relocate and construct new renal dialysis unit | Appraising | 3. FI | 2000 | 59 | 6 | 19 | 11 | 23
53 | ENV-25 | ENV-25 | Environment | Maintenance | DOID | Yes | Coastal Protection Program | Coastal Protection Program (CPP) | To Inspect the condition of the 11 existing ripraps around the island and perform maintenance/repairs where necessary. | Planned | 3. FI | 2000 | 56 | 3 | 6 | 30 | 17
45 | ENV-13 | ENV-25 | Environment | New | DOID | No | Coastal Protection Program | CPP: Renewal of Seawalls (Aiwo Hotel) | Construction renewal of existing Seawalls at the rear of Aiwo Hotel | Planned | 3. FI | 396 | 56 | 3 | 6 | 30 | 17
46 | ENV-14 | ENV-25 | Environment | New | DOID | No | Coastal Protection Program | CPP: Renewal of Seawalls (north of new port - 82m) | Construction renewal of existing Seawalls immediately North of Nauru Port | Planned | 3. FI | 492 | 56 | 3 | 6 | 30 | 17
47 | ENV-15 | ENV-25 | Environment | New | DOID | No | Coastal Protection Program | CPP: Renewal of Seawalls (north from new port - 386m) | Construction renewal of existing Seawalls North of the Nauru Port | Planned | 3. FI | 2316 | 56 | 3 | 6 | 30 | 17
48 | ENV-16 | ENV-25 | Environment | New | DOID | No | Coastal Protection Program | CPP: Renewal of Seawalls (Menen Hotel - 414ms) | Construction renewal of existing Seawalls near the Menen Hotel | Planned | 3. FI | 2484 | 56 | 3 | 6 | 30 | 17
49 | ENV-17 | ENV-25 | Environment | New | DOID | No | Coastal Protection Program | CPP: Construction of Seawalls (Anetan locations) | Construction of new Seawalls - ANETAN (59 Metres) | Appraising | 3. FI | 324.5 | 56 | 3 | 6 | 30 | 17
51 | ENV-19 | ENV-25 | Environment | New | DOID | No | Coastal Protection Program | CPP: Construction of Seawalls (Anibere locations) | Construction of new Seawalls - ANIBARE (40 Metres) | Appraising | 3. FI | 220 | 56 | 3 | 6 | 30 | 17
52 | ENV-27 | ENV-25 | Environment | Maintenance | DOID | No | Coastal Protection Program | CPP: Repairs to Existing Seawalls (riprap) | To Inspect the condition of the 11 existing ripraps around the island and perform maintenance/repairs where necessary. | Planned | 3. FI | 770 | 56 | 3 | 6 | 30 | 17
23 | EMG-11 | EMG-11 | Emergency | Purchase | NES | No |  | Replacement of Fire Trucks | Airport categorisation is about to change with the purchase of the new 737-800 cargo plane. Fire service cannot currently meet the requirements of this categorisation. Existing fire trucks are old and access to parts is becoming a major issue | Planned | 3. FI | 2000 | 53 | 16 | 3 | 11 | 23
140 | WAS-13 | WAS-13 | WaterSewer | New | NUC-W | No |  | Water Storage Tank Upgrade | Expanding Storage Capacity. Rehab 3 million L water storage tank and 2 x 300,000 L water treatment tanks for B-13 site - materials on island - need a new contractor | Planned | 3. FI | 350 | 53 | 13 | 6 | 17 | 17
83 | LAN-16 | LAN-13 | Land | Renewal | DOID | No | Capital Repairs to Sealed Road Program | SRRP: Rehabilitation of Boe School Access Road | Capital repairs to base pavement, surface seal and drainage of approximately 315 m road length providing access to Boe Infant School | Planned | 3. FI | 250 | 51 | 9 | 12 | 14 | 16
84 | LAN-17 | LAN-13 | Land | Renewal | DOID | No | Capital Repairs to Sealed Road Program | SRRP: Improving Drainage on Ring Road | Capital repairs to the drainage system, including repairs and/or capacity increase of about 25 soak pits and addition of drain pipes to soak pits where capacity of soak areas is limited | Planned | 3. FI | 750 | 51 | 9 | 12 | 14 | 16
85 | LAN-18 | LAN-13 | Land | Maintenance | DOID | No | Capital Repairs to Sealed Road Program | SRRP: Capital Repairs to Roadside Curbs and Drainage | To inspect the condition of roadside curbs, driveways and gutters around the ring road and to perform repairs/renewal where needed | Planned | 3. FI | 250 | 51 | 9 | 12 | 14 | 16
116 | PUB-17 | PUB-17 | PublicBuilding | Tech. Assist. | PSA | No |  | Master Plan to Consolidate Government Buildings | Master plan for redevelopment of the main admin building, possibly relocation to high ground, and green energy. Also consolidation of government buildings into one area. | Planned | 3. FI | 400 | 49 | 6 | 0 | 17 | 26
32 | ENE-13 | ENE-13 | Energy | New | NUC-E | No | High Voltage 11KV Grid Extention | RPC 2 Grid Extension | Source funding to connect HV Grid Extension on Government infrastructure at topside that are currently energised by stand alone gensets | Planned | 3. FI | 900 | 48 | 9 | 6 | 17 | 16
79 | JUS-13 | JUS-13 | Justice | Upgrade | NPF | No | Nauru Police - Repairs and Upgrade of buildings | Upgrading the Police Training College | To repair the current state of the current Police Training Cente, as the actual building is at the stage of collapse and has become a major OHS issue for employees. The current building is over 20 years old, the current buidling is in urgent need for major repairs such as, change of walls, painting, ceiling replacments, electrical works, water capturing system and tank, as well as the Police Gym | Planned | 3. FI | 500 | 48 | 9 | 16 | 4 | 19
81 | LAN-14 | LAN-14 | Land | Upgrade | DOID | No |  | Barrier Railing – Airport Ring Road | Renewal and Construction of 820LM of new Armco Barrier to Airport ring road. | Planned | 3. FI | 529 | 47 | 6 | 9 | 12 | 20
145 | LAN-30 | LAN-30 | Land | New | DEMA | No |  | Extension of Menen Farm | DEMA is in the process of working with UNDP to access $2m from China's Global Development South South Cooperation Fund to construct the necessary infrastructure to install climate smart agricultural technologies on site | Planned | 3. FI | 2000 | 45 | 16 | 12 | 7 | 10
112 | PUB-13 | PUB-13 | PublicBuilding | Upgrade | NFMRA | No |  | Refurbishment of Aquaculture Holding Centre |  | Planned | 3. FI | 1000 | 44 | 19 | 6 | 11 | 8
40 | ENE-23 | ENE-23 | Energy | New | NUC-E | No |  | Acquire New 16m Cherry Picker | Acquisition of specialist vehicle to enable safe working around distribution pylons | Planned | 3. FI | 250 | 43 | 10 | 6 | 4 | 23
100 | MAR-12 | MAR-12 | Maritime | New | NMPA | No | Sustainable and Climate-Resilient Connectivity Project | Heavy Lifting Solution - Crane | Heavy Lifting Solution - Crane for new tugboat (donated through JICS) as part of Nauru Port Development Project. | Appraising | 3. FI | 4500 | 42 | 12 | 3 | 11 | 16
115 | PUB-11 | PUB-11 | PublicBuilding | Renewal | PSA | No |  | Recon. of Internal Affairs Buildings at Mennen Hill | Reconstruction of internal affairs buildings located on Mennen Hill, including child protection and counselling, tourism office, domestic violence shelter, Nauru Cultural center and Youth Affairs Services Buidlings | Planned | 3. FI | 1300 | 34 | 3 | 12 | 6 | 13
137 | WAS-16 | WAS-16 | WaterSewer | Upgrade | DCCNR | Yes | Nauru Sustainable Urban Development Program | Nauru Sustainable Urban Development Program | Implement improvements in water supply, sanitation and solid waste management from Master Plan | Appraising | 4. CP | 60156.25 | 56 | 13 | 6 | 17 | 20
141 | WAS-19 | WAS-16 | WaterSewer | New | NUC-W | No | Nauru Sustainable Urban Development Program | NSUDP: Water Supply Pipeline | Reticulation and Reservoirs for households | Appraising | 4. CP | 37400 | 56 | 13 | 6 | 17 | 20
142 | WAS-20 | WAS-16 | WaterSewer | New | NUC-W | No | Nauru Sustainable Urban Development Program | NSUDP: Sanitation Upgrade | System for treatment of sludge from septic tanks to produce nitrogen rich compost for land reclamation | Appraising | 4. CP | 28000 | 56 | 13 | 6 | 17 | 20
80 | LAN-13 | LAN-13 | Land | Renewal | DOID | Yes | Capital Repairs to Sealed Road Program | Capital Repairs to Sealed Road Program (SRRP) | Resealing and Repairs to Existing Roads | Planned | 4. CP | 14000 | 51 | 9 | 12 | 14 | 16
| Row Labels | Count of Proj. Ref.
| DCCNR | 1
| DEMA | 1
| DOH | 3
| DOID | 14
| DOS | 8
| DOT | 1
| NES | 1
| NFMRA | 1
| NMPA | 1
| NPF | 3
| NUC-E | 6
| NUC-W | 3
| PSA | 2
| TVET | 3
| Grand Total | 48

## Definition
Nauru Strategic Infrastructure Investment Plan
BUILDING A 5-10 YEAR REGISTER (LIST) OF INVESTMENT PROJECTS
A. Purpose
The government of Nauru is compiling a centralised database of all committed, planned and proposed capital projects across Nauru's primary sectors (listed below). This consolidated database will allow cabinet to establish a funding and investment strategy to ensure our investment program is sustainably managed. In order to complete this activity we are asking agencies(1) responsible for managing infrastructure across these sectors to provide a list of candidate projects likely to require funding over the next 5-10 years. Some of these projects will already be underway and some may only be at an early inception or feasibility stage. Our database is designed to capture them all.
Note: (1) Implementing Agency is the line ministry or other government agency or SOE responsible for the capital investment (budgeting). (2) Known infrastructure related investments likely to start in the next 10 years shuld be entered (given feasibility, appraisal, funding and design of these project can take many years). Other investments should be forecast out as far is as practical (ideally 5 years)
(Note: shaded rows only accept valide entries from the dropdown validation list)
ID | FIELD | FIELD DESCRIPTION | LIST VALUES | LIST DESCRIPTION | Scroll Down ---->
1 | Reference Number | Any unique project reference that is used internally or within financial systems to reference ongoing or budgeted projects. | (text) | Where an existing unique system reference is not available leave blank
2 | Additional Funding Required? | Flag unfunded projects/programs that may require funding outside of your normal budget allocation. | Yes | Requires additional funding support (Special project, large development, etc)
|  |  | No | Project likely to be funded under normal budget allocation
3 | Sector | The primary sector the investment is associated with. This is not always same as the main sector the department operates in. | Land | Transport - Land
|  |  | Aviation | Transport - Air
|  |  | Maritime | Transport - Maritime
|  |  | Energy | Utilities - Energy
|  |  | WaterSewer | Utilities - Water and Sanitation
|  |  | ICT | Utilities - Telecom and ICT
|  |  | Waste | Utilities - Solid Waste and Reclamation
|  |  | Education | Community - Education
|  |  | Health | Community - Healthcare and Disability
|  |  | Cultural | Community - Community and Cultural
|  |  | Recreation | Community - Sports and Recreation
|  |  | Justice | Security and Commerce - Police and Justice
|  |  | Emergency | Security and Commerce - Emergency Services
|  |  | PublicBuilding | Security and Commerce - Public Administration
|  |  | Environ | Security and Commerce - Coastal and Environment
|  |  | Industry | Security and Commerce - Commerce and Industry
4 | Project Type | Defines the 'primary' nature of the investment, whether it is to build, rehabilitate or improve existing infrastructure or purchase new equipment etc. When the project is associated with more than one type of investment then select the predominant. | New Constrn. | Build new capital construction
|  |  | Upgrade | Upgrade or improve existing capacity of expand extent
|  |  | Renewal | Refurbish or replace existing (like with like)
|  |  | Tech. Assist. | Studies and designs associated with infrastructure or capital works (e.g. feasibility study, monitoring).
|  |  | Purchase | Capital purchase of plant/equipment/machinery
5 | Asset Class | The predominant asset the project relates to | (list) | Choose from list of asset classes
6 | Budget Entity | The entity who has budget responsibility | (list) | Choose from list of ministries/agencies
7 | Lead Unit | The department or unit responsible for project delivery | (text) | Enter department name/acronym
8 | Program Level Budget Entry? | Programs cover many sites, can be recurrent, and generally relate to renewing existing infrastructure (e.g. road rehabilitation, town centre upgrade, bridge replacements, pipe renewals) | Yes | Program budget line (see examples)
|  |  | No | Defined project (can be within a program)
9 | Program Name | Brief program title | (text) | (leave blank if project not part of program)
10 | Project Name | Brief project title | (text) | (leave blank if program header)
11 | Brief Description | Brief description which will help people understand the broad scope of the project/program. | (text) | Keep brief (less than 3 lines of text)
12 | Status of Project | The stage the project is at in the delivery cycle. | Ongoing | Ongoing and multi-year, funded, in budget
|  |  | Budgeted | Yet to start, funding secured, in budget
|  |  | Appraising | Unfunded, not in budget, submitted to MFEM, currently being evaluated
|  |  | Planned | Unfunded, not in budget, not yet submitted to MFEM or evaluated
13 | Latest Estimate ($) | Best estimate of the total investment (If a recurrent program specify the 'annual' allocation and comment in Column#19) | (numeric) | Budget in funding currency (e.g. USD, NZD)
14 | Currency | The currency of the estimate | (list) | Don't convert to aud if estimate is in another currency
15 | Likely Funding From | Actual or best estimate of the likely budget source(s) from which the project will be funded. If multiple sources place 'X' in the relevant columns. If donor is known specific in Column#16. | Agency | Funding likely from agencies own revenue and capital budget
|  |  | Government | Funding likely from government grant
|  |  | Donor | Funding likely from donor (e.g. WBG, ADB, MFAT, DFAT, USAID, JICA etc)
|  |  | Private | Private funding source (e.g. church, community, commercial entity)
16 | Secured funding from | For 'Funded' projects where development partners providing funding please name the donor(s) | (text) | If bi-lateral agreements name all partners. Use notes field to break out contribution if known
17 | Cost Estimate (AUD$,000) | The cost estimate (Column#13) converted to $,000 AUD | (formula) | Calculated field - do not edit
18 | Estimated/Actual Start Year | The calendar year the investment commenced (ongoing) or is expected to commence (budgeted-planned) | (integer) | (Calendar Year)
19 | Notes | Any notes on progress or of interest to add further context about the project, its status, or source of information. | (text)
20 | Added by | Name/initials of person who entered the row/record | (text)
21 | Identified in | File name or description of where the project was identified (e.g. Asset management plan, corporate plan, capital projects spreadsheet). | (text) | Include file reference if from a list

## Codes
Below are the list of codes used in this workbook - additional codes can be added in the clear cells
Code | 2019 NIISP Status
Completed | Project complete
Ongoing | Project started but not complete
Appraising | Actively seeking funding for next budget
Unfunded | Still in pipeline
Discarded | No longer a valid project
Unknown | Not aware of project as described
Code | Project type
R | Rehabilitation or repair infrastructure
U | Upgradeor improvement infrastructure
N | New infrastructure
E | Equipment procurement or replacement
O | Other
Code | DEPARTMENT
CIE | Dept of Commerce, Industry and Environment
CENPAC | CENPAC Teleco Provider
DCA | Department of Civil Aviation
DCCNR | Department of Climate Change & National Resilience
DOID | Department of Infrastructure Development
DLS | Department of Land and Survey Management
DOET | Department of Education and Training
DOF | Department of Finance
DOH | Department of Health
DOJ | Departmentof Justice
DOM | Department of Media
DOS | Department of Sport
DOT | Department of Transport
ICT | ICT Department
MPS | Ministry of Public Services
NEC | National Emergency Services
NES | Nauru Emergency Services
NFMRA | Fisheries & Marine Resources
NMPA | Nauru Maritime and Ports Authority
NPF | Nauru Police Force
NRC | Nauru Rehabilitation Corporation
NUC-E | Nauru Utilities Corporation (Energy)
NUC-W | Nauru Utilities Corporation (Water)
PAD | Planning and Aid Division (DOF)
PSA | Public Services Administration
TVET | Nauru Vocational Training Centre (DOE)
VEI | Vital Energy Incorporated
DEMA | Department of Environmental Management & Agriculture
Code | SECTOR
Land | Transport - Land | LAN
Aviation | Transport - Air | AIR
Maritime | Transport - Maritime | MAR
Energy | Utilities - Energy | ENE
WaterSewer | Utilities - Water and Sanitation | WAS
ICT | Utilities - Telecom and ICT | ICT
Waste | Utilities - Solid Waste and Reclamation | SWA
Education | Community - Education | EDU
Health | Community - Healthcare and Disability | HEA
Cultural | Community - Community and Cultural | COM
Recreation | Community - Sports and Recreation | SPO
Justice | Security and Commerce - Police and Justice | JUS
Emergency | Security and Commerce - Emergency Services | EMG
PublicBuilding | Security and Commerce - Public Administration | PUB
Environment | Security and Commerce - Coastal and Environment | ENV
Industry | Security and Commerce - Commerce and Industry | IND
Code | PROJECT TYPE
New | Build new capital construction
Upgrade | Upgrade or improve existing capacity of expand extent
Renewal | Refurbish or replace existing (like with like)
Maintenance | Routine or periodic maintenance
Tech. Assist. | Studies and designs associated with infrastructure or capital works (e.g. feasibility study, monitoring).
Purchase | Capital purchase of plant/equipment/machinery
Other | Other project type
Code | ASSET TYPE
Boats and Vessels
Bridges
Buildings
Coastal Protection
Footpaths
Heavy Equipment
Housing
Motor Vehicles
Multi-Asset
Navigation Aids
Other Assets
Pipelines
Reclamation
Reservoirs
Runway Pavements
Sealed Roads
Septic Tanks
Sewerage Treatment
Solar Power
Specialty Equipment
Specialty Vehicles
Storage Tanks
Stormwater
Towers and ICT
Transmission lines
Unknown (tbd)
Unsealed Roads
Water Treatment
Wharfs and Jetties
Code | STATUS
Ongoing | Ongoing and multi-year, funded, in budget
Budgeted | Yet to start, funding secured, in budget
Appraising | Unfunded, not in budget, submitted to MFEM, currently being evaluated
Planned | Unfunded, not in budget, not yet submitted to MFEM or evaluated
Code | LIKELY FUNDING SOURCE
Agency | Funding likely from agencies own revenue and capital budget
Gov. Grant | Funding likely from government grant
Donor | Funding likely from donor (e.g. WBG, ADB, MFAT, DFAT, USAID, JICA etc)
Private | Private funding source (e.g. church, community, commercial entity)
Code | CURRENCY
AUD | 1
USD | 0.64
NZD | 1.08
EUR | 0.59
JPY | 94.1

## MCA (v2.1)
MCA Ref | Proj No | Project | Lead Unit | Est. (million) | 1.1 | 1.2 | 1.3 | 2.1 | 2.2 | 2.3 | 3.1 | 3.2 | 3.3 | 4.1 | 4.2 | 4.3 | Total score | Economy | Social | Environment | Efficiency
14 | ENV-21 | Higher Ground Initiative Program | Other Assets | 100 | 10 | 6 | 10 | 3 | 3 | 10 | 10 | 10 | 10 | 10 | 7 | 10 | 99 | 26 | 16 | 30 | 27
19 | SPO-14 | Micronesian Games 2026 - Stadium and Land | Buildings | 8 | 10 | 6 | 0 | 3 | 10 | 10 | 4 | 10 | 10 | 10 | 7 | 6 | 86 | 16 | 23 | 24 | 23
21 | SPO-12 | Micronesian Games 2026 Program (Other) | Multi-Asset | 14.5 | 10 | 6 | 0 | 3 | 10 | 10 | 4 | 10 | 10 | 10 | 7 | 6 | 86 | 16 | 23 | 24 | 23
18 | EDU-25 | TVET Multi-Purpose Workshop | Buildings | 5 | 6 | 6 | 6 | 10 | 3 | 10 | 7 | 6 | 7 | 10 | 7 | 3 | 81 | 18 | 23 | 20 | 20
9 | HEA-19 | Redevelopment of RON Hospital | Buildings | 93 | 10 | 6 | 0 | 3 | 10 | 6 | 7 | 0 | 7 | 10 | 10 | 6 | 75 | 16 | 19 | 14 | 26
6 | AIR-11 | Nauru Airport Terminal Redevelopment Program | Buildings | 20 | 10 | 10 | 0 | 0 | 3 | 6 | 7 | 3 | 4 | 10 | 10 | 7 | 70 | 20 | 9 | 14 | 27
2 | ENE-14 | Buada LV Undergroung Cabling Replacement | Transmission lines | 1.2 | 6 | 3 | 3 | 3 | 3 | 0 | 7 | 10 | 4 | 10 | 10 | 10 | 69 | 12 | 6 | 21 | 30
16 | EDU-21 | TVET Hospitality Workshop | Buildings | 3 | 3 | 10 | 6 | 10 | 6 | 10 | 7 | 0 | 4 | 3 | 4 | 6 | 69 | 19 | 26 | 11 | 13
17 | EDU-24 | TVET Industrial Workshop | Buildings | 3 | 3 | 6 | 3 | 10 | 3 | 10 | 7 | 3 | 4 | 10 | 4 | 6 | 69 | 12 | 23 | 14 | 20
26 | ENE-19 | 3.3kV Switchgear Circuit Breaker upgrade | Other Assets | 1.102 | 10 | 6 | 6 | 3 | 3 | 0 | 7 | 0 | 7 | 10 | 10 | 6 | 68 | 22 | 6 | 14 | 26
27 | ENE-20 | Upgrade Power Transformers - RMN, RME and RMS | Other Assets | 1.396 | 10 | 6 | 6 | 3 | 3 | 0 | 7 | 0 | 7 | 10 | 10 | 6 | 68 | 22 | 6 | 14 | 26
13 | ENE-18 | Location 3.3kv Sub-Station | Transmission lines | 1.5 | 10 | 7 | 3 | 3 | 3 | 0 | 10 | 0 | 4 | 10 | 7 | 10 | 67 | 20 | 6 | 14 | 27
22 | JUS-11 | Nauru Police Repairs and Upgrade of Police Buildings | Buildings | 0.2 | 10 | 6 | 0 | 10 | 3 | 6 | 2 | 3 | 4 | 6 | 7 | 10 | 67 | 16 | 19 | 9 | 23
8 | HEA-18 | Redevelopment of Naoero Public Health Center | Buildings | 53 | 10 | 3 | 0 | 3 | 10 | 6 | 7 | 0 | 4 | 6 | 10 | 6 | 65 | 13 | 19 | 11 | 22
23 | JUS-12 | Maritime Police Unit | Specialty Equipment | 0.5 | 3 | 6 | 10 | 3 | 3 | 6 | 7 | 0 | 7 | 3 | 7 | 10 | 65 | 19 | 12 | 14 | 20
28 | WAS-21 | Meneng RO Project | Other Assets | 0.1 | 10 | 3 | 6 | 0 | 10 | 3 | 10 | 0 | 4 | 6 | 7 | 6 | 65 | 19 | 13 | 14 | 19
20 | SPO-19 | Micronesian Games 2026 - Training, Competition & Gym Equip. | Specialty Equipment | 2.5 | 10 | 3 | 0 | 3 | 10 | 10 | 4 | 3 | 2 | 6 | 7 | 6 | 64 | 13 | 23 | 9 | 19
24 | ENV-23 | Establishment of Seawall Behind Central Police Station | Coastal Protection | 0.4 | 3 | 3 | 3 | 0 | 6 | 3 | 10 | 3 | 7 | 6 | 10 | 10 | 64 | 9 | 9 | 20 | 26
7 | ENE-22 | Tank Farm Assets Renewal | Storage Tanks | 1.5 | 10 | 10 | 3 | 3 | 3 | 3 | 7 | 0 | 7 | 6 | 7 | 3 | 62 | 23 | 9 | 14 | 16
40 | LAN-15 | Rehabilitation of Embassy Hill Road and Access roads | Sealed Roads | 2 | 6 | 3 | 0 | 0 | 3 | 3 | 7 | 10 | 10 | 10 | 7 | 3 | 62 | 9 | 6 | 27 | 20
10 | HEA-14 | Renal Dialysis Unit | Buildings | 2 | 6 | 0 | 0 | 3 | 10 | 6 | 7 | 0 | 4 | 10 | 7 | 6 | 59 | 6 | 19 | 11 | 23
35 | WAS-16 | Nauru Sustainable Urban Development Project | Multi-Asset | 60.1562 | 10 | 0 | 3 | 0 | 3 | 3 | 10 | 0 | 7 | 10 | 4 | 6 | 56 | 13 | 6 | 17 | 20
38 | ENV-25 | Coastal Protection Programme | Coastal Protection | 2 | 3 | 0 | 0 | 0 | 3 | 3 | 10 | 10 | 10 | 10 | 4 | 3 | 56 | 3 | 6 | 30 | 17
43 | HEA-13 | New Pharmacy and Medical Supplies Warehouse | Buildings | 2.5 | 10 | 0 | 0 | 0 | 10 | 0 | 7 | 0 | 4 | 10 | 7 | 6 | 54 | 10 | 10 | 11 | 23
5 | AIR-13 | Backup Generator for the Nauru International Airport | Specialty Equipment | 0.12 | 10 | 6 | 3 | 0 | 3 | 3 | 4 | 0 | 2 | 6 | 10 | 6 | 53 | 19 | 6 | 6 | 22
34 | WAS-13 | Water Storage Tank Upgrade | Reservoirs | 0.35 | 10 | 0 | 3 | 0 | 3 | 3 | 10 | 0 | 7 | 10 | 4 | 3 | 53 | 13 | 6 | 17 | 17
36 | EMG-11 | Replacement of Fire Trucks | Specialty Vehicles | 2 | 10 | 6 | 0 | 0 | 3 | 0 | 7 | 0 | 4 | 10 | 7 | 6 | 53 | 16 | 3 | 11 | 23
4 | LAN-13 | Resealing and Repair of Existing Roads | Sealed Roads | 14 | 6 | 3 | 0 | 3 | 6 | 3 | 4 | 6 | 4 | 6 | 4 | 6 | 51 | 9 | 12 | 14 | 16
25 | ENV-24 | Land Reclamation and Development | Reclamation | 0.07 | 3 | 3 | 6 | 0 | 0 | 6 | 6 | 10 | 7 | 3 | 3 | 3 | 50 | 12 | 6 | 23 | 9
30 | PUB-17 | Masterplan for Government Buildings | Buildings | 0.4 | 6 | 0 | 0 | 0 | 0 | 0 | 10 | 3 | 4 | 6 | 10 | 10 | 49 | 6 | 0 | 17 | 26
44 | HEA-12 | New Wellness Centers (Yaren, Anibar & NPHC) | Buildings | 7.5 | 6 | 0 | 0 | 3 | 10 | 3 | 4 | 0 | 4 | 6 | 7 | 6 | 49 | 6 | 16 | 8 | 19
11 | WAS-18 | Household Water Storage Tanks | Storage Tanks | 0.2 | 6 | 0 | 3 | 0 | 6 | 3 | 10 | 0 | 4 | 6 | 4 | 6 | 48 | 9 | 9 | 14 | 16
39 | JUS-13 | Upgrading of the Police Training Center | Buildings | 0.5 | 6 | 3 | 0 | 10 | 0 | 6 | 2 | 0 | 2 | 6 | 7 | 6 | 48 | 9 | 16 | 4 | 19
41 | ENE-13 | RPC 2 Grid Extension | Transmission lines | 0.9 | 6 | 3 | 0 | 0 | 6 | 0 | 4 | 6 | 7 | 6 | 4 | 6 | 48 | 9 | 6 | 17 | 16
37 | LAN-14 | Barrier Railing - Airport Ring Road | Sealed Roads | 0.529 | 6 | 0 | 0 | 0 | 6 | 3 | 2 | 6 | 4 | 10 | 7 | 3 | 47 | 6 | 9 | 12 | 20
3 | HEA-17 | Construction of Disability Rehabilitation Centre | Buildings | 0.3 | 6 | 0 | 0 | 3 | 10 | 3 | 2 | 0 | 2 | 6 | 7 | 6 | 45 | 6 | 16 | 4 | 19
12 | PUB-19 | Smart House | Housing | 2.355 | 6 | 0 | 0 | 3 | 6 | 3 | 7 | 0 | 7 | 3 | 4 | 6 | 45 | 6 | 12 | 14 | 13
1 | PUB-13 | Refurbishment of Aquaculture Holding Facilities | Buildings | 1 | 3 | 6 | 10 | 0 | 3 | 3 | 7 | 0 | 4 | 0 | 2 | 6 | 44 | 19 | 6 | 11 | 8
31 | ENE-23 | New 16 metre Cherry Picker | Specialty Vehicles | 0.25 | 10 | 0 | 0 | 0 | 3 | 3 | 2 | 0 | 2 | 10 | 7 | 6 | 43 | 10 | 6 | 4 | 23
29 | MAR-12 | New Travel/Boat Lift | Specialty Equipment | 4.5 | 6 | 3 | 3 | 0 | 0 | 3 | 7 | 0 | 4 | 6 | 4 | 6 | 42 | 12 | 3 | 11 | 16
42 | ICT-16 | Repairs to High Value Equipment | Towers and ICT | 0.15 | 6 | 0 | 0 | 3 | 6 | 3 | 2 | 0 | 2 | 6 | 7 | 6 | 41 | 6 | 12 | 4 | 19
15 | ICT-12 | Sustainable power supply through renewable energy for Media Building | Towers and ICT | 0.2 | 3 | 0 | 0 | 3 | 0 | 3 | 7 | 0 | 4 | 6 | 7 | 6 | 39 | 3 | 6 | 11 | 19
32 | PUB-22 | PSA Office Development and Renovation | Buildings | 0.02 | 3 | 0 | 0 | 3 | 0 | 0 | 10 | 0 | 2 | 3 | 7 | 6 | 34 | 3 | 3 | 12 | 16
33 | PUB-11 | Reconstruction of Internal Affairs Buildings (Mennen Hill) | Buildings | 1.3 | 3 | 0 | 0 | 3 | 6 | 3 | 2 | 0 | 4 | 3 | 7 | 3 | 34 | 3 | 12 | 6 | 13
145 | LAN-30 | Extension of Menen Farm | Other Assets | 2 | 3 | 3 | 10 | 3 | 6 | 3 | 0 | 3 | 4 | 0 | 7 | 3 | 45 | 16 | 12 | 7 | 10